## Epics
SlNo | Epics | Userstories | Description | Column4 | Priority | Size (S, M, L, XL) | Description/ Dependancy | Sprint (Relative) | Column1 | Sprints | Column2 | Column3
1 | Case Management (project) |  |  |  | 0
1.01 |  | Create/modify a project/case | add/edit: title, description, amount, currency, commission. |  |  | 3 |  |  | Commission setup, title, description, associated beneficiary |  | 1
|  | List and View a case - for beneficiary | my cases: title, photo, total donated - view, edit (no pagination,no file upload, only bind the link rom DB) view: title, photo, summary, total donated, amount. Commission | As Beneficiary, I must be able to list down my cases created by me. As Beneficiary, I must be able to detailed view case created by me. |  | 3
1.02 |  | Workflow - Draft => Publish => Maturity => Closed => Obsolete (TBD) | Draft - Edit, Publish - Readonly, Closed - Readonly, Obsolete - Admin/owner make it obsolete. Created case will initially mark as draft and draft case can be edited by the ower. Ownere will be able to publithe case when it is in draft state. Once case id published state, the case will be come readonly. Ownere will be abele to mark it as obsolete when the case is in Draft and/or Published. Published/Obsolete will make case as readonly. | As Beneficiary, I must be able to mark my case as Published. As Beneficiary, I must be able to mark my case as Obsolete. As Beneficiary, I must be able to edit only case which is in Draft. |  | 2 |  |  |  |  | 1 | draft publish
1.03 |  | Preview a draft project/case - nice to have - dependancy with details page |  | As Beneficiary, I must be able to preview a case. |  | 3 |  |  | Display of commission setup, title, description, associated beneficiary
1.04 |  | Details View - Same - preview must use this screen layout | Title, Decription, Photos, Beneficiary details-photo,name,&commission, Donation Received | As visitor, I must be able to view details of a case. |  | 5 |  |  |  |  | 1
1.05 |  | Commission setup - as part of create and edit, view |  |  |  | 0
1.06 |  | Comments - flat | TBD | As visitor, I must be able to view and provide comments for a case by FB credentials. |  | 2
1.07 |  | Conversation - hierarchical | TBD
1.08 |  | Rating - (Review rate score, display rating average) | Show average rating, Show overlay to rate newly - rating and description can be provided and submited. (add/edit user rating) Only logedin user can rate a case. Otehrwise user will be asked to login. | As a visitor, I must be able to view average rating of a case. As a registered user, I must be able to rate a case along with description. As a registered user, I must be able to override my rating and rating description. |  | 5 |  |  | Rate star and a shortdescription |  | 2
1.09 |  | Rating history | Show review history below case content, reviews will be paginated (show more). clicking on rating count will be navigating the control to bottom of case content were the rating history displayed. | As a visitor, I must be able to view rating history and description. |  | 3 |  |  |  |  | 2
1.1 |  | Report abuse | only storing it on DB, only loged in user will be able to mark as abuse. Same user will be an update to the earlier comment. This is action for administrator. Admin function will need to take seperately. | As a registered user, I must be able to report a case as not genuine/abuse. |  | 2 |  |  |  |  | 2
1.11 |  | Share on social media - FB/Instagram/WhatsApp | Place FB share and Like button on case | As a visitor, I must be able to Like and/or share a case on Facebook/Instagram. |  | 2
1.12 |  | Like on social media - FB/Instagram/WhatsApp | NA - like and share can be done togather with 2 pointers
1.13 |  | Location and searchability | While creating the case, beneficiary should be abel to provide the location (address with all fields). Allow to change the location using pin from map, and store lat long in ddatabase. Location must be dieplayed on preview and case details page - with address on baloon. searchability not pat of this estimation. | As a Beneficiary, I must be able to provide geo location while creating a case. As a Beneficiary, I must be able to set and adjust geo location from map based on the address while creating a case so that it will be displayed in case page while viewing or previewing. |  | 3 |  |  |  |  | 2
1.14 |  | Upload Photos | Upload photos of a case, mark one are primary. Allow rearranging. Primary photo will be hoswin on tile. User should be able to remove added photo. There will be size limit. No picture adjustment feature required as part of this userstory. | As a Beneficiary, I must be able to upload photos of a case. As a Beneficiary, I must be able to rearrange photos uploaded. As a Beneficiary, I must be able to set a photo as primary. |  | 5 |  |  | Upload, Size, diamention, simple edit, cover photo, limit. |  | 2
1.15 |  | Upload Video, video url. | TBD, video url | [5 empty] | Upload, size, url?
1.16 |  | List - Recent and top rated. Relevant, Latest, popular,Top-rated, Location (near by), pagination | Home Page, filter: Published. Sort: Recent and top rated. Pagination. Pagination expands the list in home page itself. Filter/search is not part of this userstory. Fields: Title, Photo, Description, Beneficiary Name and photo, location. Caseid, beneficaryid. | As a visitor, I must be able to view list of published cases on home page. As a visitor, I must be able to view list of published cases on home page sorted by recent and top rated and paginated. |  | 5 |  |  | Define the scope |  | 2
1.17 |  | Donation - List, Total, lookup | Assume donation is already done. With this userstory we have to list the donations. Donor name, photo and donated amount, city and country name. x donors will be showin intially and howed more when clicking on show more. sort: donated amount | As a visitor, I must be able to view list of donors for a particular case. As a visitor, I must be able to view list of donors for a particular case sorted by donation amount.. |  | 3
1.18 |  | Payment options accepted | While creating a case, the beneficiary must opt the payment methodsaccepted. - TBD, needed clarity
1.19 |  | QR Code | N/A
1.2 |  | KYCs - specific to case | N/A
2 | Beneficiary Management |  |  |  | 1
2.01 |  | Beneficiary Register | N/A | [7 empty] | 2
2.02 |  | Profile view edit (my story), manage cases - Beneficiary listing. | Beneficiary: My story, benefactor:loan reason, occupationb, social media link. Part of profile edit and view profile | As a beneficiary, I must be able to provide my story which will be displayed to the site visitors on public profile. As a benefactor, I must be able to provide social media links which will be displayed to site visotors on public profile. As a benefactor, I must be able to provide 'loan reason' which will be displayed to site visotors on public profile. As a visitor, I must be able to view Beneficiary profile for a case. As a visitor, I must be able to view Benefactor/Donor profile for a case. |  | 2 |  |  |  |  | 3
2.03 |  | Beneficiary KYC management for payment options | N/A
2.04 |  | Beneficiary Profile public view | required | [7 empty] | 3
|  | Beneficiary Rating | Similar to case rating | As a visitor, I must be able to view average rating of a Beneficiary. As a registered user, I must be able to rate a beneficiary along with description. As a registered user, I must be able to override my rating and rating description for a beneficiary. As a visitor, I must be able to view rating history and description for a beneficiary. |  | 3
|  | Contact Beneficiary | Sending email to beneficiary, loged in suer data can be prefilled, but public user have to provide all details, in MVP no storing for contact us details. |  |  | 2
2.05 |  | Beneficiary Transaction tractability | TBD
2.05 |  | Beneficiary Contact me - email | TBD | [7 empty] | 3
3 | Benefactor Management |  |  |  | 1
3.01 |  | Benefactor Register
3.02 |  | Benefactor Profile edit (description), cases | [8 empty] | 2
3.03 |  | Benefactor Profile public view | [8 empty] | 3
3.04 |  | Benefactor Transaction tractability | required
3.05 |  | Benefactor Contact me - email | TBD | [7 empty] | 3
4 | Profile Management (common) |  |  |  | 1
4.01 |  | Login |  |  |  | 9 | M |  |  |  | 1
4.02 |  | Thirdparty login (FB, Goolge) | pavan |  | p:9,a:8,o:10(20),s:16-20+3 | 9 | L | 3 |  |  | 2
4.03 |  | Register | atul/om |  | a:5,o:(12),p:7(9),s:16-18 | 9 |  |  |  |  | 1
4.04 |  | Activate |  |  |  | 9 | S | 1 |  |  | 2
4.05 |  | View profile | om/atul/pavan |  | a:6,o:5,p:8,s:8 | 9 | M |  |  |  | 3
4.06 |  | Change Password |  |  |  | 9 |  |  |  |  | 3
4.07 |  | Forgot Password |  |  | a:8,p:12,o:12,s:16 | 9 |  |  |  |  | 3
5 | Customer Support |  | Happy fox |  | 3 | 28.6364 | p:5,a:5,o:7 |  |  |  | 5
5.01 |  | CS Submit a case - for customer support
5.02 |  | CS Conversation
5.03 |  | CS Chat Support
6 | Donation |  |  |  | 2 | [5 empty] | 4
6.01 |  | Donation breakdown/charges | [6 empty] | min max?, limit,
6.02 |  | Donation - inward
6.03 |  | Donation - payout (2 transactions)
6.04 |  | Transaction tractability
6.05 |  | Payment options - TBD | bitcoin
TBD Functional
7 |  | Non Functional
7.01 | Theme |  |  |  | 0 | [5 empty] | 0
7.01.1 |  | Color
7.01.2 |  | Fonts
7.01.3 |  | Logo, background image, etc.
7.01.4 |  | Title, Tagline, Texts
7.02 | Localization |  |  |  | 0 | [5 empty] | 0
7.02.1 |  | TBD
7.03 | File handling |  | IPFS |  | 0 | [5 empty] | 0
7.03.1 |  | TBD
7.04 | Spike on payment options |  |  |  | 0 | [5 empty] | 3
7.04.1 |  | TBD
7.05 | Logging |  |  |  | 1
7.05.1 |  | TBD
7.06 | Exception Handling |  |  |  | 1 | [5 empty] | 3
7.06.1 |  | TBD
7.07 | Authentication and Authorization |  |  |  | 0 | [5 empty] | 0
7.07.1 |  | Passport authentication
7.08 | Template handling - Email |  |  |  | 2 | [5 empty] | 3
7.08.1 |  | TBD
7.09 | Payment Gateway - multi tenancy |  |  |  | 1 |  |  |  | only case and related data wil be isolated |  | 3
7.09.1 |  | TBD
7.1 | Multi-tenancy - support |  |  |  | 1 | [5 empty] | 0
7.1.1 |  | TBD
7.2 | TBD Non Functional |  |  |  | 2

## Events
Pre kickoff (Thursday, 2019-JUN-12) | JUN12 - JUN21
1. Walkthrough of identified epics and userstories |  |  | User Self Service | Register | Login | Forgot Password | Change Password | Profile Edit
2. Set the priority/stack ranking |  |  | Beneficiary | Public Profile
3. Brainstorm for initial 3 sprints epics and userstories – a draft only |  |  | Benefactor | Public Profile
4. Breakdown during discussion if possible |  |  | Case | Create | Edit | View | List | Workflow | Review/Rating
Phase 0: Design phase (3-4 weeks, may extend also) | JUN17 - JUL12 |  | KYC Handling | Upload KYCs | Vew KYCs | KYC Workflow
1. Architecture design (ongoing) | MEANS |  | Payment | Methods | Payment | View | History | Logs
2. Infrastructure – identify Prod, Dev | AWS/S3 |  | Customer Support | Create Ticket | View Ticket | Ticket Workflow
3. Feasibility of technical required component(s) only | Inprogress |  | Tenant
4. Low level design for required component(s) only | Inprogress
5. Brainstorm for initial 3 sprints epics and userstories (2-3 iteration is possible) – finalization | Pending
6. Backlog grooming – reprioritize, identify the spikes, do further breakdown, size the user story | Pending
7. Framework development (at least mandatory components must be finished, rest all can be taken later in sprints as spikes) | Inprogress
Phase 1 onwards – sprints (2 weeks, iterative sprints)
1. Sprint planning and identify the goal | JUN12 - JUL19
2. Daily scrum/standup
3. Backlog grooming – reprioritize, identify the spikes, do further breakdown
4. Sprint review/demo
5. Sprint retrospective
Sprint 1 | JUL22 - AUG09 | Case listing, case view, beneficiary view, benefactor view
Sprint 2 | JUL12 - AUG30 | Case Onboarding, Show Location, Rate and Review, Show rating history, Donors and Donation Received
Sprint 3 | SEP02 - AUG20 | Case Upload and preview photos, discussion (FB), case-social media like and share, Payment-Cryptocurrency, QA
QA, Bugfixes
Sprint 4 | SEP23 - OCT11 | Payment integration pendings, Bug fixes, UAT
QA, UAT, Bugfixes
Sprint 5 | OCT14 - OCT31 | Support

## references
oauth | Passport | http://www.passportjs.org/docs/

## Sheet6
admin tool
list recent cases
list marked as abuse
transaction tracability
|  | 0.5 | 1 | 2 | 3 | 5 | 8
|  | XS | S | M | L | XL | XXL
| min h | 1 | 3 | 5 | 8 | 13 | 21
| max h | 3 | 5 | 8 | 13 | 21 | 34
|  | XS | S | M | L | XL | XXL
| min h | 3 | 5 | 8 | 13 | 21 | 34
| max h | 5 | 8 | 13 | 21 | 34 | 55
variance

## Sprint01
Sprint 01
| 2019-07-24 | 2019-07-25 | 2019-07-26 | 2019-07-27 | 2019-07-28 | 2019-07-29 | 2019-07-30 | 2019-07-31 | 2019-08-01 | 2019-08-02 | 2019-08-03 | 2019-08-04 | 2019-08-05 | 2019-08-06 | Bandwidth | Other/leaves
Athul | [14 empty] | 80 | 0 | bar: 2019-07-24 to 2019-08-06
Pavan | 1 | 1 | 0.5 |  |  | 0.5 | 0.5 | 1 | 1 | 1 |  |  | 1 | 1 | 68 | 12
Om | 1 | 1 | 1 |  |  | 1 | 1 | 1 | Leave | Leave |  |  | 1 | 1 | 64 | 16
Shiju | 1 | 1 | 1 |  |  | Leave | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 72 | 8
[15 empty] | 284 | 36
View list of cases - Injest cases and supporting data from back end | [15 empty] | Shiju |  | 2019-07-31 | bar: 2019-07-24 to 2019-07-26; 2019-07-29
As a visitor, I must be able to view list of published cases on home page. | [15 empty] | Om/Pavan | Athul | bar: 2019-07-24 to 2019-07-26; 2019-07-29
As a visitor, I must be able to view location of a case from home screen up on selecting the map button from case tile view. | [15 empty] | Om/Pavan | Athul | bar: 2019-07-29
As a visitor, I must be able to view list of published cases on home page sorted by recent and top rated and paginated. | [15 empty] | Om/Pavan | Athul | bar: 2019-07-26; 2019-07-29 to 2019-07-30
As visitor, I must be able to view details of a case. | [15 empty] | Shiju/Pavan | Athul | bar: 2019-07-26; 2019-07-29 to 2019-07-30; 2019-08-02
As visitor, I must be able to view map location for case in case details view. | [15 empty] | Shiju/Pavan | Athul | bar: 2019-08-02
As visitor, I must be able to view photos in case details view. | [15 empty] | Om/Pavan | Athul | bar: 2019-07-29 to 2019-07-30; 2019-08-06
As a visitor, I must be able to view average rating of a case. | [15 empty] | Shiju/Pavan | Athul | bar: 2019-07-30 to 2019-08-01; 2019-08-06
As a visitor, I must be able to view list of donors for a particular case. | [15 empty] | Om/Pavan | Athul | bar: 2019-07-30 to 2019-07-31; 2019-08-05
As a visitor, I must be able to view rating history and description. | [15 empty] | Shiju/Pavan | Athul | bar: 2019-08-02; 2019-08-05 to 2019-08-06
As a visitor, I must be able to view list of donors for a particular case sorted by donation amount.. | [15 empty] | Om/Pavan | Athul | bar: 2019-08-05 to 2019-08-06
Deliery date
In-Progress
Sprint planning meeting | 2019-07-24: 2019-07-24
| 10:00 | 11:00
Fill details in userstory/feature
Assignment
Delivery plan
View list of cases - Injest cases and supporting data from back end
As a visitor, I must be able to view list of published cases on home page.
As a visitor, I must be able to view location of a case from home screen up on selecting the map button from case tile view.
As a visitor, I must be able to view list of published cases on home page sorted by recent and top rated and paginated.
As visitor, I must be able to view details of a case.
As visitor, I must be able to view map location for case in case details view.
As visitor, I must be able to view photos in case details view.
As a visitor, I must be able to view average rating of a case.
As a visitor, I must be able to view list of donors for a particular case.
As a visitor, I must be able to view rating history and description.
As a visitor, I must be able to view list of donors for a particular case sorted by donation amount..

## Sprint02
|  | 2019-08-07 | 2019-08-08 | 2019-08-09 | 2019-08-10 | 2019-08-11 | 2019-08-12 | 2019-08-13 | 2019-08-14 | 2019-08-15 | 2019-08-16 | 2019-08-17 | 2019-08-18 | 2019-08-19 | 2019-08-20 | Bandwidth | Other/leaves
| Athul | [14 empty] | 64 | 16 | bar: 2019-08-07 to 2019-08-08; 2019-08-12 to 2019-08-14; 2019-08-16; 2019-08-19 to 2019-08-20
| Pavan | [14 empty] | 64 | 16 | bar: 2019-08-07 to 2019-08-08; 2019-08-12 to 2019-08-14; 2019-08-16; 2019-08-19 to 2019-08-20
| Om | [14 empty] | 64 | 16 | bar: 2019-08-07 to 2019-08-08; 2019-08-12 to 2019-08-14; 2019-08-16; 2019-08-19 to 2019-08-20
| Shiju | [14 empty] | 64 | 16 | bar: 2019-08-07 to 2019-08-08; 2019-08-12 to 2019-08-14; 2019-08-16; 2019-08-19 to 2019-08-20
[16 empty] | 256 | -176
51 | As a visitor, I must be able to view rating history and description. | bar: 2019-08-07 to 2019-08-08; 2019-08-12
105 | Show 3 dots "..." at the end instead of the description is cut off on list view - home page | bar: 2019-08-08
106 | As a user, i must be able to view the map either location or an area in a map | [14 empty] | shiju | bar: 2019-08-12 to 2019-08-13
107 | Completed - Another status for published | [14 empty] | om | bar: 2019-08-12 to 2019-08-13
45 | As a visitor, I must be able to view Beneficiary profile for a case - basic details. | [14 empty] | shiju | bar: 2019-08-13 to 2019-08-14; 2019-08-16
46 | As a visitor, I must be able to view Benefactor/Donor profile for a case. - basic details | [14 empty] | shiju | bar: 2019-08-13 to 2019-08-14; 2019-08-16
108 | As a visitor, I must be able to view Beneficiary profile for a case - cases managed | [14 empty] | om | bar: 2019-08-16; 2019-08-19
113 | As a visitor, I must be able to view Benefactor/Donor profile for a case. - loans and cases | [14 empty] | om | bar: 2019-08-16; 2019-08-19
109 | As a visitor, I must be able to view Beneficiary profile for a case - rating | [14 empty] | shiju | bar: 2019-08-19 to 2019-08-20
110 | As a visitor, I must be able to view Beneficiary profile for a case - Social media | [14 empty] | shiju | bar: 2019-08-19 to 2019-08-20
111 | As a visitor, I must be able to view Beneficiary profile for a case - verified list | [14 empty] | shiju | bar: 2019-08-19 to 2019-08-20
112 | As a visitor, I must be able to view Beneficiary profile for a case - contact me | [14 empty] | om | bar: 2019-08-20
114 | As a visitor, I must be able to view Benefactor/Donor profile for a case. - Contact me | [14 empty] | om | bar: 2019-08-20

## Sprint03
|  | 2019-08-21 | 2019-08-22 | 2019-08-23 | 2019-08-24 | 2019-08-25 | 2019-08-26 | 2019-08-27 | 2019-08-28 | 2019-08-29 | 2019-08-30 | 2019-08-31 | 2019-09-01 | 2019-09-02 | 2019-09-03 | Bandwidth | Other/leaves
| Athul | [14 empty] | 72 | 8 | bar: 2019-08-21 to 2019-09-03
| Pavan | [14 empty] | 72 | 8 | bar: 2019-08-21 to 2019-09-03
| Om | [14 empty] | 72 | 8 | bar: 2019-08-21 to 2019-09-03
| Shiju | 1 | 1 | 0 |  |  | 0 | 0 | 1 | 1 | 1 |  |  |  | 1 | 48 | 32
[16 empty] | 264 | -184
167 | Spike on contact me | [14 empty] | om | pavan,atul | bar: 2019-08-23 to 2019-08-25; 2019-08-31 to 2019-09-02
50 | As a visitor, I must be able to view average rating of a Beneficiary. - Spike on UI | [15 empty] | pavan,atul | bar: 2019-08-22; 2019-08-24 to 2019-08-25; 2019-08-31 to 2019-09-02
156 | Social media links to be opened on new tab - UI | [15 empty] | pavan,atul | bar: 2019-08-21; 2019-08-24 to 2019-08-25; 2019-08-31 to 2019-09-02
157 | Map display area issue - and address on balloon | [15 empty] | pavan,atul | bar: 2019-08-22 to 2019-08-25; 2019-08-31 to 2019-09-02
158 | open popup screen for review history - UI | [15 empty] | pavan,atul | bar: 2019-08-24 to 2019-08-26; 2019-08-31 to 2019-09-02
159 | As a registered user, I must be able to rate a case along with description. | [14 empty] | shiju | pavan,atul | bar: 2019-08-24 to 2019-08-25; 2019-08-27; 2019-08-31 to 2019-09-02
160 | As a registered user, I must be able to override my rating and rating description. - backend | [14 empty] | shiju | pavan,atul | bar: 2019-08-24 to 2019-08-25; 2019-08-27; 2019-08-31 to 2019-09-02
161 | As Beneficiary, I must be able to list down my cases created by me. | [14 empty] | om | pavan,atul | bar: 2019-08-24 to 2019-08-25; 2019-08-28; 2019-08-31 to 2019-09-02
162 | As Beneficiary, I must be able to mark my case as Published. | [14 empty] | om | pavan,atul | bar: 2019-08-24 to 2019-08-25; 2019-08-29; 2019-08-31 to 2019-09-02
163 | As Beneficiary, I must be able to view case details created by me. | [14 empty] | om | pavan,atul | bar: 2019-08-24 to 2019-08-25; 2019-08-30 to 2019-09-02
164 | As Beneficiary, I must be able to create a case | [14 empty] | shiju | pavan,atul | bar: 2019-08-24 to 2019-08-25; 2019-08-31 to 2019-09-03
165 | As a Beneficiary, I must be able to upload photos of a case. | [14 empty] | om | pavan,atul | bar: 2019-08-24 to 2019-08-25; 2019-08-31 to 2019-09-03
166 | As a Beneficiary, I must be able to set a photo as primary - crop and rearrange | [14 empty] | om | pavan,atul | bar: 2019-08-24 to 2019-08-25; 2019-08-31 to 2019-09-03
170 | Rearrange the code proper way repository/domain business logic and service separation based on domain | [14 empty] | om | bar: 2019-08-24 to 2019-08-25; 2019-08-31 to 2019-09-03
171 | Rearrange the code proper way components, directive, pipes and service separation based on domain | [14 empty] | pavan | bar: 2019-08-24 to 2019-08-25; 2019-08-31 to 2019-09-03
172 | Deployment environment proposal and procure test server | [14 empty] | shiju | bar: 2019-08-24 to 2019-08-25; 2019-08-31 to 2019-09-03
Atul:
Well:
Wrong:
Improvement:
1. Could have help pavan in api integration/angular part
2. Testing could have done
3: More syncups
Tarun:
Well:
1. Following practices
Wrong:
Improvement:
1. Callout blockage at earlier stage
2. Problem of understanding then and there we must improvise
3. Dry run one day before
Om
Well
Wrong:
1. Testing not done properly
2. Confusion in userstories
3. Took lots of userstories
Improvement:
Pavan:
Well:
Wrong:
Improvement:
1. Communication needed improvement
Shiju
[18 empty] | Well | Team done a hardwork though there were leaves. Try best to manage well
[18 empty] | Wrong | Took lots of user stories than is suppose to be.
Assumption -
Done was not done -
Spill overs are keep on increasing
Taking testing activity - knowning begining of the sprint
Velosity
Pavan is fully loaded
Improvement:
Ownership, Donot close userstory

## Sprint04
|  | 2019-09-04 | 2019-09-05 | 2019-09-06 | 2019-09-07 | 2019-09-08 | 2019-09-09 | 2019-09-10 | 2019-09-11 | 2019-09-12 | 2019-09-13 | 2019-09-14 | 2019-09-15 | 2019-09-16 | 2019-09-17 | Bandwidth | Other/leaves
| Athul | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 1 | 72 | 8
| Pavan | [14 empty] | 80 | 0 | bar: 2019-09-04 to 2019-09-06; 2019-09-09 to 2019-09-13; 2019-09-16 to 2019-09-17
| Om | [14 empty] | 80 | 0 | bar: 2019-09-04 to 2019-09-06; 2019-09-09 to 2019-09-13; 2019-09-16 to 2019-09-17
| Shiju | 0.5 | 0.5 | 0.5 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  |  | 0.5 | 0.5 | 40 | 40
[16 empty] | 272 | -192
217 | After Successful creation of case must be displayed in my cases of beneficiary profile | 2019-09-05: shiju |  | shiju
218 | Displaying the success message to user on successful creation of case | 2019-09-05: atul |  | atul
219 | Email validation - on contact me and register user etc | [15 empty] | pavan | bar: 2019-09-04
220 | After rating the case rating should be displayed in rating and review history | [15 empty] | om | bar: 2019-09-05
221 | Displaying the Address in pop up of Map | 2019-09-05: atul |  | atul
222 | Map region must be on all map views not only front page (even case details view) | 2019-09-05: pavan |  | pavan
223 | Publish button in Edit case (for making the case publish) - publish and validate mandatory fields | [15 empty] | om | bar: 2019-09-06
224 | Alternate for displaying the photo of case if case photo is not provided- we need alternate | 2019-09-06: atul |  | atul
225 | email send issue, we will try to get CC SMTP details from thorkild | 2019-09-09: shiju |  | shiju
226 | My case should have 'View' option to view and edit a case | [15 empty] | atul | bar: 2019-09-04
165 | As a Beneficiary, I must be able to upload photos of a case. | 2019-09-09: pavan |  | pavan/om
166 | As a Beneficiary, I must be able to set a photo as primary - and rearrange | [15 empty] | atul/pavan/om | bar: 2019-09-11
228 | As Beneficiary, I must be able to edit a case | [15 empty] | shiju/atul | bar: 2019-09-13
170 | Rearrange the code proper way repository/domain business logic and service separation based on domain | [15 empty] | om | bar: 2019-09-16
171 | Rearrange the code proper way components, directive, pipes and service separation based on domain | [15 empty] | pavan | bar: 2019-09-16
227 | Research on Theme - if any improvement can be done | [15 empty] | atul | bar: 2019-09-17
172 | Deployment environment proposal and procure test server | [15 empty] | shiju | bar: 2019-09-17
[19 empty] | What went well | Want went not well | Improvement
[18 empty] | Atul | Took less number of tasks, and were able to manage. Everyone know wha to be done this time Proper testing by the team was done | Tasks were too less, we could take more | Take more tasks as streach goal
[18 empty] | Pavan | This time we had idntified issues/queries happened earlier stage itself Proper syncup - improved | Took less tasks Every Team Involvement in planning userstories and activities Need everyones involvement, currently not involved. Only shiju is doing it | Better give this role to every one and try it
[18 empty] | Om | Perform tasks faster then previous sprints. US was simple Proper syncup done, morethen 2 or 3 times | Some of the userstories, clear doubts in sprint planning itself. | Time of sprint planning itself improvement have to be done
[18 empty] | Shiju | We had taken corrective action and able to demo previous sprint and current sprint successfully. Given very good demo. | Not questions were asked while sprint planning meetings There were some descrepencies in understanding and were clear last mement. Assumptions were made indivisually and not shared during any syncups. Technical tasks are not taken seriously, this impact quality of the code base. | involvement of sprint planing needs improved. Asking questions needs improment. Assumptions must be clarified at earlier stage of sprint, if any. Needed equal importance for technical userstories and finish in sprint itself.
[18 empty] | Tarun |  |  | Team need to raise the concern in syncup, needs improvement Above needs to be clarified then and there in syncup meettings.

## Sprint05
|  | 2019-09-18 | 2019-09-19 | 2019-09-20 | 2019-09-21 | 2019-09-22 | 2019-09-23 | 2019-09-24 | 2019-09-25 | 2019-09-26 | 2019-09-27 | 2019-09-28 | 2019-09-29 | 2019-09-30 | 2019-10-01 | Bandwidth | Other/leaves
| Athul | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 0 | 1 |  |  | 1 | 1 | 72 | 8
| Pavan | 1 | 1 | 0.5 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 76 | 4
| Om | [14 empty] | 80 | 0 | bar: 2019-09-18 to 2019-09-20; 2019-09-23 to 2019-09-27; 2019-09-30 to 2019-10-01
| Shiju | [14 empty] | 80 | 0 | bar: 2019-09-18 to 2019-09-20; 2019-09-23 to 2019-09-27; 2019-09-30 to 2019-10-01
[16 empty] | 308 | -228
271 | As a beneficiary I must be able to remove a photo from a case | [15 empty] | pavan/om | bar: 2019-09-19
272 | The case tile view must show thumbnail photo | [15 empty] | shiju/pavan | bar: 2019-09-24
273 | The case view must show original photo on selection from image thumbnail scroll view | [15 empty] | shiju/atul | bar: 2019-09-25
274 | Uploaded photo must be stored as original and thumbnail photo on storage | [15 empty] | shiju | bar: 2019-09-23
275 | Upload a photo for registered user | [15 empty] | om/atul | bar: 2019-09-26
276 | Data change warning to user | [15 empty] | pavan/om | bar: 2019-09-27
277 | Google address search suggestion to user | [15 empty] | pavan/shiju | bar: 2019-09-30
278 | As a Beneficiary, I must be able to upload photos and rearrange photo of a published case. | [15 empty] | pavan/om | bar: 2019-09-27
170 | Rearrange the code proper way repository/domain business logic and service separation based on domain | [15 empty] | om | bar: 2019-10-01
171 | Rearrange the code proper way components, directive, pipes and service separation based on domain | [15 empty] | pavan | bar: 2019-10-01
227 | Research on Theme - if any improvement can be done | [15 empty] | atul | bar: 2019-10-01
172 | Deployment environment proposal and procure test server | [15 empty] | shiju | bar: 2019-10-01

## Sprint04-works
Project: commoncollection Server: http://tfs.blocktech.dk/tfs/blocktech Query: commoncollection Team - Sprint 4 - Backlog List type: Flat
ID | Title | Work Item Type | State | Assigned To | Remaining Work
217 | After Successful creation of case must be displayed in my cases of beneficiary profile | Bug | New | Shiju Madamchery
218 | Displaying the success message to user on successful creation of case | Bug | New | Atul Kandyong
219 | Email validation - on contact me and register user etc | Bug | New | Pavan Kulkarni
220 | After rating the case rating should be displayed in rating and review history | Bug | New | Omkar Sai Sunku
221 | Displaying the Address in pop up of Map | Bug | New | Atul Kandyong
222 | Map region must be on all map views not only front page (even case details view) | Bug | New | Pavan Kulkarni
223 | Publish button in Edit case (for making the case publish) - publish and validate mandatory fields | Bug | New | Omkar Sai Sunku
224 | Alternate for displaying the photo of case if case photo is not provided- we need alternate | Bug | New | Atul Kandyong
225 | email send issue, we will try to get CC SMTP details from thorkild | Bug | New | Shiju Madamchery
226 | My case should have 'View' option to view and edit a case | Bug | New | Atul Kandyong
165 | As a Beneficiary, I must be able to upload photos of a case. | Product Backlog Item | Approved | Omkar Sai Sunku
166 | As a Beneficiary, I must be able to set a photo as primary - and rearrange | Product Backlog Item | Approved
228 | As Beneficiary, I must be able to edit a case | Product Backlog Item | New
170 | Rearrange the code proper way repository/domain business logic and service separation based on domain | Product Backlog Item | New
171 | Rearrange the code proper way components, directive, pipes and service separation based on domain | Product Backlog Item | New
227 | Research on Theme - if any improvement can be done | Product Backlog Item | New | Atul Kandyong
172 | Deployment environment proposal and procure test server | Product Backlog Item | New

## Todo in future sprints
S.NO | Description todo in future sprints
1 | Rating and reviews should not be allowed to same case holder/beneficiary.
2 | Display ratings and reviews in rating and review popup if already rated by a specific user. Helps when user overriding his/her ratings

## seed.data.user
ID | tenantId | email | phone | firstName | lastName | latitude | longitude | addressLine1 | addressLine2 | place | city | state | country | pincode | ratingCount | ratingOn | accountId | description | occupation | social | JSON
01 | cc | shiju@blocktech.dk | 9686622751 | Shiju | Madamchery | 13.1186 | 77.5975 | Outskirts | Halli | Yelanka | Bangalore | Karnataka | India | 560099 | 0 | 2009-07-20T10:00:15 | QjYjsYmmuWPhYxt8hGjKx3cRH841rNv7w1 | I am a Software Architect and Project Manager with 14+ years of experience in cloud, IoT, Blockchain, .net technologies. Worked over 60 projects of small scale to enterprise solutions. Currently focused in Blockchain, IoT, and cloud based solutions. | Software Architect | [ {code: "FB", text: "https://www.facebook.com/shiju.prakasan" } ] | let user01 = { tenantId: 'cc', email: 'shiju@blocktech.dk', phone: '9686622751', language: Languages.US, role: RoleTypes.Standard, basic: { userId: 'shiju@blocktech.dk', firstName: 'Shiju', lastName: 'Madamchery', profilePhoto: 'shiju_profile_photo', language: Languages.US.toString(), } as UserLite, address: { addressLine1: 'Outskirts', addressLine2: 'Halli', city: 'Yelanka', country: 'India', language: Languages.US, pincode: '560099', place: 'Bangalore', state: 'Karnataka' } as Address, location: { latitude: 13.1186, longitude: 77.5975 },authProviders: [{ provider: AuthProviders.Local, phash: 'tobecreated', userid: 'shiju@blocktech.dk' } as UserAuthProvider], verification: { activated: true, emailVerified: true, phoneVerified: true } as UserVerification, reqProfile: { description: "I am a Software Architect and Project Manager with 14+ years of experience in cloud, IoT, Blockchain, .net technologies. Worked over 60 projects of small scale to enterprise solutions. Currently focused in Blockchain, IoT, and cloud based solutions.", socialMedialLinks: [ {code: "FB", text: "https://www.facebook.com/shiju.prakasan" } ] },rating: { count: 0, recentUpdate: new Date('2009-07-20T10:00:15'), average: 0 },accounts: [{ accountId: 'QjYjsYmmuWPhYxt8hGjKx3cRH841rNv7w1', accountType: PaymentTypes.BTC } as CryptoAccount] } as BeneficiaryUser;
02 | cc | pavan@blocktech.dk | 9686622751 | Pavan | Kumar | 17.4222 | 78.4416 | 8-2-409,Rd number2 | Green Valley | Banjara Hills | Hyderabad | Telangana | India | 500034 | 0 | 2009-07-20T10:00:16 | QjYjsYmmuWPhYxt8hGjKx3cRH841rNv7w1 | I am a Software Developer with 2+ years of experience in .net technologies. Currently focused in Blockchain, Angular, React and cloud based solutions. | Software Developer | [ {code: "FB", text: "https://www.facebook.com/pavan.kulkarni.92505" } ] | let user02 = { tenantId: 'cc', email: 'pavan@blocktech.dk', phone: '9686622751', language: Languages.US, role: RoleTypes.Standard, basic: { userId: 'pavan@blocktech.dk', firstName: 'Pavan', lastName: 'Kumar', profilePhoto: 'pavan_profile_photo', language: Languages.US.toString(), } as UserLite, address: { addressLine1: '8-2-409,Rd number2', addressLine2: 'Green Valley', city: 'Banjara Hills', country: 'India', language: Languages.US, pincode: '500034', place: 'Hyderabad', state: 'Telangana' } as Address, location: { latitude: 17.4222, longitude: 78.4416 },authProviders: [{ provider: AuthProviders.Local, phash: 'tobecreated', userid: 'pavan@blocktech.dk' } as UserAuthProvider], verification: { activated: true, emailVerified: true, phoneVerified: true } as UserVerification, reqProfile: { description: "I am a Software Developer with 2+ years of experience in .net technologies. Currently focused in Blockchain, Angular, React and cloud based solutions.", socialMedialLinks: [ {code: "FB", text: "https://www.facebook.com/pavan.kulkarni.92505" } ] },rating: { count: 0, recentUpdate: new Date('2009-07-20T10:00:16'), average: 0 },accounts: [{ accountId: 'QjYjsYmmuWPhYxt8hGjKx3cRH841rNv7w1', accountType: PaymentTypes.BTC } as CryptoAccount] } as BeneficiaryUser;
03 | cc | atul@blocktech.dk | 9686622751 | Atul | Kandyyog | 18.5204 | 73.8567 | Hadapsar Industrial Estate | Pune- Solapur Road | Hadapsar | Pune | Maharashtra | India | 411013 | 0 | 2009-07-20T10:00:17 | QjYjsYmmuWPhYxt8hGjKx3cRH841rNv7w1 | I am a Design Engineer with 5+ years of experience in UX designing. Currently focused in Blockchain, Angular, React and cloud based solutions. | Design Engineer | [ {code: "FB", text: "https://www.facebook.com/atul.kandyong" } ] | let user03 = { tenantId: 'cc', email: 'atul@blocktech.dk', phone: '9686622751', language: Languages.US, role: RoleTypes.Standard, basic: { userId: 'atul@blocktech.dk', firstName: 'Atul', lastName: 'Kandyyog', profilePhoto: 'atul_profile_photo', language: Languages.US.toString(), } as UserLite, address: { addressLine1: 'Hadapsar Industrial Estate', addressLine2: 'Pune- Solapur Road', city: 'Hadapsar', country: 'India', language: Languages.US, pincode: '411013', place: 'Pune', state: 'Maharashtra' } as Address, location: { latitude: 18.5204, longitude: 73.8567 },authProviders: [{ provider: AuthProviders.Local, phash: 'tobecreated', userid: 'atul@blocktech.dk' } as UserAuthProvider], verification: { activated: true, emailVerified: true, phoneVerified: true } as UserVerification, reqProfile: { description: "I am a Design Engineer with 5+ years of experience in UX designing. Currently focused in Blockchain, Angular, React and cloud based solutions.", socialMedialLinks: [ {code: "FB", text: "https://www.facebook.com/atul.kandyong" } ] },rating: { count: 0, recentUpdate: new Date('2009-07-20T10:00:17'), average: 0 },accounts: [{ accountId: 'QjYjsYmmuWPhYxt8hGjKx3cRH841rNv7w1', accountType: PaymentTypes.BTC } as CryptoAccount] } as BeneficiaryUser;
04 | cc | tarun@blocktech.dk | 9686622751 | Tarun | Kumar | 17.3901 | 78.472 | 5-8,56/A | Nampally Station Road | Abids | Hyderabad | Telangana | India | 500001 | 0 | 2009-07-20T10:00:18 | QjYjsYmmuWPhYxt8hGjKx3cRH841rNv7w1 | I am a General Manager with 10+ years of experience. Currenctly focusing on Blockchain. | General Manager | [ {code: "FB", text: "https://www.facebook.com/shiju.prakasan" } ] | let user04 = { tenantId: 'cc', email: 'tarun@blocktech.dk', phone: '9686622751', language: Languages.US, role: RoleTypes.Standard, basic: { userId: 'tarun@blocktech.dk', firstName: 'Tarun', lastName: 'Kumar', profilePhoto: 'tarun_profile_photo', language: Languages.US.toString(), } as UserLite, address: { addressLine1: '5-8,56/A', addressLine2: 'Nampally Station Road', city: 'Abids', country: 'India', language: Languages.US, pincode: '500001', place: 'Hyderabad', state: 'Telangana' } as Address, location: { latitude: 17.3901284, longitude: 78.4719723 },authProviders: [{ provider: AuthProviders.Local, phash: 'tobecreated', userid: 'tarun@blocktech.dk' } as UserAuthProvider], verification: { activated: true, emailVerified: true, phoneVerified: true } as UserVerification, reqProfile: { description: "I am a General Manager with 10+ years of experience. Currenctly focusing on Blockchain.", socialMedialLinks: [ {code: "FB", text: "https://www.facebook.com/shiju.prakasan" } ] },rating: { count: 0, recentUpdate: new Date('2009-07-20T10:00:18'), average: 0 },accounts: [{ accountId: 'QjYjsYmmuWPhYxt8hGjKx3cRH841rNv7w1', accountType: PaymentTypes.BTC } as CryptoAccount] } as BeneficiaryUser;
05 | cc | gauthami@blocktech.dk | 9686622751 | Gauthami | BT | 20.9301 | 78.5877 | 7 St. George | Il-Belt Valletta | San Anton Gardens | Balzan | Attard | Malta | 4005 | 0 | 2009-07-20T10:00:19 | QjYjsYmmuWPhYxt8hGjKx3cRH841rNv7w1 | I am a HR Manager and Assistant Secretary with 3+ years of experience. Currectly focused on Blockchain and finding freshers and experienced professional to our company for Blockchain development projects | HR Manager and Assistant Secretary | [ {code: "FB", text: "https://www.facebook.com/shiju.prakasan" } ] | let user05 = { tenantId: 'cc', email: 'gauthami@blocktech.dk', phone: '9686622751', language: Languages.US, role: RoleTypes.Standard, basic: { userId: 'gauthami@blocktech.dk', firstName: 'Gauthami', lastName: 'BT', profilePhoto: 'gauthami_profile_photo', language: Languages.US.toString(), } as UserLite, address: { addressLine1: '7 St. George', addressLine2: ' Il-Belt Valletta', city: 'San Anton Gardens', country: 'Malta', language: Languages.US, pincode: '4005', place: 'Balzan', state: 'Attard' } as Address, location: { latitude: 20.9301487, longitude: 78.5877228 },authProviders: [{ provider: AuthProviders.Local, phash: 'tobecreated', userid: 'gauthami@blocktech.dk' } as UserAuthProvider], verification: { activated: true, emailVerified: true, phoneVerified: true } as UserVerification, reqProfile: { description: "I am a HR Manager and Assistant Secretary with 3+ years of experience. Currectly focused on Blockchain and finding freshers and experienced professional to our company for Blockchain development projects", socialMedialLinks: [ {code: "FB", text: "https://www.facebook.com/shiju.prakasan" } ] },rating: { count: 0, recentUpdate: new Date('2009-07-20T10:00:20'), average: 0 },accounts: [{ accountId: 'QjYjsYmmuWPhYxt8hGjKx3cRH841rNv7w1', accountType: PaymentTypes.BTC } as CryptoAccount] } as BeneficiaryUser;
06 | cc | rashmi@blocktech.dk | 9686622751 | Rashmi | BT | 23.9301 | 73.5877 | Outskirts | Halli | Yelanka | Bangalore | Karnataka | India | 560104 | 0 | 2009-07-20T10:00:20 | QjYjsYmmuWPhYxt8hGjKx3cRH841rNv7w1 | I am a Test Engineer with 2+ years of experience. Willing to work in a challenging and responsible position as an Engineer in an organization where I can contribute to its successful growth using my abilities and skills and further improve my personal and professional skills. | Test Engineer |  | let user06 = { tenantId: 'cc', email: 'rashmi@blocktech.dk', phone: '9686622751', language: Languages.US, role: RoleTypes.Standard, basic: { userId: 'rashmi@blocktech.dk', firstName: 'Rashmi', lastName: 'BT', profilePhoto: 'rashmi_profile_photo', language: Languages.US.toString(), } as UserLite, address: { addressLine1: 'Outskirts', addressLine2: 'Halli', city: 'Yelanka', country: 'India', language: Languages.US, pincode: '560104', place: 'Bangalore', state: 'Karnataka' } as Address, location: { latitude: 23.9301487, longitude: 73.5877228 },authProviders: [{ provider: AuthProviders.Local, phash: 'tobecreated', userid: 'rashmi@blocktech.dk' } as UserAuthProvider], verification: { activated: true, emailVerified: true, phoneVerified: true } as UserVerification, donorProfile: { description: "I am a Test Engineer with 2+ years of experience. Willing to work in a challenging and responsible position as an Engineer in an organization where I can contribute to its successful growth using my abilities and skills and further improve my personal and professional skills.", occupation: "Test Engineer" },rating: { count: 0, recentUpdate: new Date('2009-07-20T10:00:20'), average: 0 },accounts: [{ accountId: 'QjYjsYmmuWPhYxt8hGjKx3cRH841rNv7w1', accountType: PaymentTypes.BTC } as CryptoAccount] } as BenefactorUser;
07 | cc | om@blocktech.dk | 9686622751 | Omkar | Sai Sunku | 10.9301 | 76.5877 | Outskirts | Halli | Yelanka | Bangalore | Karnataka | India | 560105 | 0 | 2009-07-20T10:00:21 | QjYjsYmmuWPhYxt8hGjKx3cRH841rNv7w1 | I am a Software Developer and Blockchain Developer with 2+ years experience. Currenctly focusing on Blockchain, AI, ML and cloud based Solutions | Blockchain Developer | [ {code: "FB", text: "https://www.facebook.com/omkarsunku" } ] | let user07 = { tenantId: 'cc', email: 'om@blocktech.dk', phone: '9686622751', language: Languages.US, role: RoleTypes.Standard, basic: { userId: 'om@blocktech.dk', firstName: 'Omkar', lastName: 'Sai Sunku', profilePhoto: 'omkar_profile_photo', language: Languages.US.toString(), } as UserLite, address: { addressLine1: 'Outskirts', addressLine2: 'Halli', city: 'Yelanka', country: 'India', language: Languages.US, pincode: '560105', place: 'Bangalore', state: 'Karnataka' } as Address, location: { latitude: 10.9301487, longitude: 76.5877228 },authProviders: [{ provider: AuthProviders.Local, phash: 'tobecreated', userid: 'om@blocktech.dk' } as UserAuthProvider], verification: { activated: true, emailVerified: true, phoneVerified: true } as UserVerification, donorProfile: { description: "I am a Software Developer and Blockchain Developer with 2+ years experience. Currenctly focusing on Blockchain, AI, ML and cloud based Solutions", occupation: "Blockchain Developer" },rating: { count: 0, recentUpdate: new Date('2009-07-20T10:00:21'), average: 0 },accounts: [{ accountId: 'QjYjsYmmuWPhYxt8hGjKx3cRH841rNv7w1', accountType: PaymentTypes.BTC } as CryptoAccount] } as BenefactorUser;
08 | cc | suman@blocktech.dk | 9686622751 | Suman | BT | 34.9301 | 77.5123 | Outskirts | Halli | Yelanka | Bangalore | Karnataka | India | 560106 | 0 | 2009-07-20T10:00:22 | QjYjsYmmuWPhYxt8hGjKx3cRH841rNv7w1 | I am a Senior Test Engineer with 3+ years of experience. Currently focusing on .NET technologies and Blockchain. | Senior Test Engineer |  | let user08 = { tenantId: 'cc', email: 'suman@blocktech.dk', phone: '9686622751', language: Languages.US, role: RoleTypes.Standard, basic: { userId: 'suman@blocktech.dk', firstName: 'Suman', lastName: 'BT', profilePhoto: 'suman_profile_photo', language: Languages.US.toString(), } as UserLite, address: { addressLine1: 'Outskirts', addressLine2: 'Halli', city: 'Yelanka', country: 'India', language: Languages.US, pincode: '560106', place: 'Bangalore', state: 'Karnataka' } as Address, location: { latitude: 34.9301487, longitude: 77.5123 },authProviders: [{ provider: AuthProviders.Local, phash: 'tobecreated', userid: 'suman@blocktech.dk' } as UserAuthProvider], verification: { activated: true, emailVerified: true, phoneVerified: true } as UserVerification, donorProfile: { description: "I am a Senior Test Engineer with 3+ years of experience. Currently focusing on .NET technologies and Blockchain.", occupation: "Senior Test Engineer" },rating: { count: 0, recentUpdate: new Date('2009-07-20T10:00:22'), average: 0 },accounts: [{ accountId: 'QjYjsYmmuWPhYxt8hGjKx3cRH841rNv7w1', accountType: PaymentTypes.BTC } as CryptoAccount] } as BenefactorUser;
09 | cc | asha@blocktech.dk | 9686622751 | Asha | BT | 15.9301 | 77.8523 | Outskirts | Halli | Yelanka | Bangalore | Karnataka | India | 560107 | 0 | 2009-07-20T10:00:23 | QjYjsYmmuWPhYxt8hGjKx3cRH841rNv7w1 | I am a Finance and Administration Manager with 3+ years of experience | Finance and Administration Manager |  | let user09 = { tenantId: 'cc', email: 'asha@blocktech.dk', phone: '9686622751', language: Languages.US, role: RoleTypes.Standard, basic: { userId: 'asha@blocktech.dk', firstName: 'Asha', lastName: 'BT', profilePhoto: 'asha_profile_photo', language: Languages.US.toString(), } as UserLite, address: { addressLine1: 'Outskirts', addressLine2: 'Halli', city: 'Yelanka', country: 'India', language: Languages.US, pincode: '560107', place: 'Bangalore', state: 'Karnataka' } as Address, location: { latitude: 15.9301487, longitude: 77.85228 },authProviders: [{ provider: AuthProviders.Local, phash: 'tobecreated', userid: 'asha@blocktech.dk' } as UserAuthProvider], verification: { activated: true, emailVerified: true, phoneVerified: true } as UserVerification, donorProfile: { description: "I am a Finance and Administration Manager with 3+ years of experience", occupation: "Finance and Administration Manager" },rating: { count: 0, recentUpdate: new Date('2009-07-20T10:00:23'), average: 0 },accounts: [{ accountId: 'QjYjsYmmuWPhYxt8hGjKx3cRH841rNv7w1', accountType: PaymentTypes.BTC } as CryptoAccount] } as BenefactorUser;
10 | cc | annette@blocktech.dk | 9686622751 | Annette | Grothe-Moller | 16.9301 | 71.2283 | Outskirts | Halli | Yelanka | Bangalore | Karnataka | India | 560108 | 0 | 2009-07-20T10:00:24 | QjYjsYmmuWPhYxt8hGjKx3cRH841rNv7w1 | I am a Co-founder and Strategic Director has worked with psychotherapy for more than 20 years. She lives in Copenhagen with her husband. Together they have 4 children. Currently focusing on Blockchain. | Co-Founder, HR- and Strategic Director | [ {code: "FB", text: "https://www.facebook.com/annettegrothemoller" } ] | let user10 = { tenantId: 'cc', email: 'annette@blocktech.dk', phone: '9686622751', language: Languages.US, role: RoleTypes.Standard, basic: { userId: 'annette@blocktech.dk', firstName: 'Annette', lastName: 'Grothe-Moller', profilePhoto: 'annette_profile_photo', language: Languages.US.toString(), } as UserLite, address: { addressLine1: 'Outskirts', addressLine2: 'Halli', city: 'Yelanka', country: 'India', language: Languages.US, pincode: '560108', place: 'Bangalore', state: 'Karnataka' } as Address, location: { latitude: 16.9301487, longitude: 71.2282567 },authProviders: [{ provider: AuthProviders.Local, phash: 'tobecreated', userid: 'annette@blocktech.dk' } as UserAuthProvider], verification: { activated: true, emailVerified: true, phoneVerified: true } as UserVerification, donorProfile: { description: "I am a Co-founder and Strategic Director has worked with psychotherapy for more than 20 years. She lives in Copenhagen with her husband. Together they have 4 children. Currently focusing on Blockchain.", occupation: "Co-Founder, HR- and Strategic Director" },rating: { count: 0, recentUpdate: new Date('2009-07-20T10:00:24'), average: 0 },accounts: [{ accountId: 'QjYjsYmmuWPhYxt8hGjKx3cRH841rNv7w1', accountType: PaymentTypes.BTC } as CryptoAccount] } as BenefactorUser;
11 | cc | elisabeth@blocktech.dk | 9686622751 | Ellisabeth | Grothe-Moller | 11.9301 | 67.5877 | Outskirts | Halli | Yelanka | Bangalore | Karnataka | India | 560109 |  |  | QjYjsYmmuWPhYxt8hGjKx3cRH841rNv7w1 | I am a Innovation Strategist at Danske Bank with 8+ years of experience in visual design and strategy. I had actively worked in the start-up community since 2009. I have involved in many public speaking engagement and takes consulting jobs in visual design and strategy, I had wrote my first book on 'Innovative by Design - Creating Visual Design That Works’. I have done a Master's degree in Visual Culture from the University of Copenhagen. |  |  | let user11 = { tenantId: 'cc', email: 'elisabeth@blocktech.dk', phone: '9686622751', language: Languages.US, role: RoleTypes.Standard, basic: { userId: 'elisabeth@blocktech.dk', firstName: 'Ellisabeth', lastName: 'Grothe-Moller', profilePhoto: 'ellisabeth_profile_photo', language: Languages.US.toString(), } as UserLite, address: { addressLine1: 'Outskirts', addressLine2: 'Halli', city: 'Yelanka', country: 'India', language: Languages.US, pincode: '560109', place: 'Bangalore', state: 'Karnataka' } as Address, location: { latitude: 11.9301487, longitude: 67.5877228 },authProviders: [{ provider: AuthProviders.Local, phash: 'tobecreated', userid: 'elisabeth@blocktech.dk' } as UserAuthProvider], verification: { activated: true, emailVerified: true, phoneVerified: true } as UserVerification, accounts: [{ accountId: 'QjYjsYmmuWPhYxt8hGjKx3cRH841rNv7w1', accountType: PaymentTypes.BTC } as CryptoAccount] } as User;
12 | cc | karthik@blocktech.dk | 9686622751 | Karthik | BT | 12.9351 | 66.5877 | Outskirts | Halli | Yelanka | Bangalore | Karnataka | India | 560110 |  |  | QjYjsYmmuWPhYxt8hGjKx3cRH841rNv7w1 | I am a Local and Financial Director. | Local and Financial Director |  | let user12 = { tenantId: 'cc', email: 'karthik@blocktech.dk', phone: '9686622751', language: Languages.US, role: RoleTypes.Standard, basic: { userId: 'karthik@blocktech.dk', firstName: 'Karthik', lastName: 'BT', profilePhoto: 'karthik_profile_photo', language: Languages.US.toString(), } as UserLite, address: { addressLine1: 'Outskirts', addressLine2: 'Halli', city: 'Yelanka', country: 'India', language: Languages.US, pincode: '560110', place: 'Bangalore', state: 'Karnataka' } as Address, location: { latitude: 12.935147, longitude: 66.5877228 },authProviders: [{ provider: AuthProviders.Local, phash: 'tobecreated', userid: 'karthik@blocktech.dk' } as UserAuthProvider], verification: { activated: true, emailVerified: true, phoneVerified: true } as UserVerification, accounts: [{ accountId: 'QjYjsYmmuWPhYxt8hGjKx3cRH841rNv7w1', accountType: PaymentTypes.BTC } as CryptoAccount] } as User;
13 | cc | otherbt1@blocktech.dk | 9686622751 | Other1 | BT | 12.1487 | 77.5877 | Outskirts | Halli | Yelanka | Bangalore | Karnataka | India | 560111 |  |  | QjYjsYmmuWPhYxt8hGjKx3cRH841rNv7w1 |  |  |  | let user13 = { tenantId: 'cc', email: 'otherbt1@blocktech.dk', phone: '9686622751', language: Languages.US, role: RoleTypes.Standard, basic: { userId: 'otherbt1@blocktech.dk', firstName: 'Other1', lastName: 'BT', profilePhoto: 'other1_profile_photo', language: Languages.US.toString(), } as UserLite, address: { addressLine1: 'Outskirts', addressLine2: 'Halli', city: 'Yelanka', country: 'India', language: Languages.US, pincode: '560111', place: 'Bangalore', state: 'Karnataka' } as Address, location: { latitude: 12.1487, longitude: 77.5877228 },authProviders: [{ provider: AuthProviders.Local, phash: 'tobecreated', userid: 'otherbt1@blocktech.dk' } as UserAuthProvider], verification: { activated: true, emailVerified: true, phoneVerified: true } as UserVerification, accounts: [{ accountId: 'QjYjsYmmuWPhYxt8hGjKx3cRH841rNv7w1', accountType: PaymentTypes.BTC } as CryptoAccount] } as User;
14 | cc | otherbt2@blocktech.dk | 9686622751 | Other2 | BT | 12.3015 | 79.8977 | Outskirts | Halli | Yelanka | Bangalore | Karnataka | India | 560112 |  |  | QjYjsYmmuWPhYxt8hGjKx3cRH841rNv7w1 |  |  |  | let user14 = { tenantId: 'cc', email: 'otherbt2@blocktech.dk', phone: '9686622751', language: Languages.US, role: RoleTypes.Standard, basic: { userId: 'otherbt2@blocktech.dk', firstName: 'Other2', lastName: 'BT', profilePhoto: 'other2_profile_photo', language: Languages.US.toString(), } as UserLite, address: { addressLine1: 'Outskirts', addressLine2: 'Halli', city: 'Yelanka', country: 'India', language: Languages.US, pincode: '560112', place: 'Bangalore', state: 'Karnataka' } as Address, location: { latitude: 12.301487, longitude: 79.8977228 },authProviders: [{ provider: AuthProviders.Local, phash: 'tobecreated', userid: 'otherbt2@blocktech.dk' } as UserAuthProvider], verification: { activated: true, emailVerified: true, phoneVerified: true } as UserVerification, accounts: [{ accountId: 'QjYjsYmmuWPhYxt8hGjKx3cRH841rNv7w1', accountType: PaymentTypes.BTC } as CryptoAccount] } as User;
15 | cc | otherbt3@blocktech.dk | 9686622751 | Other3 | BT | 12.9301 | 75.1242 | Outskirts | Halli | Yelanka | Bangalore | Karnataka | India | 560113 |  |  | QjYjsYmmuWPhYxt8hGjKx3cRH841rNv7w1 |  |  |  | let user15 = { tenantId: 'cc', email: 'otherbt3@blocktech.dk', phone: '9686622751', language: Languages.US, role: RoleTypes.Standard, basic: { userId: 'otherbt3@blocktech.dk', firstName: 'Other3', lastName: 'BT', profilePhoto: 'other3_profile_photo', language: Languages.US.toString(), } as UserLite, address: { addressLine1: 'Outskirts', addressLine2: 'Halli', city: 'Yelanka', country: 'India', language: Languages.US, pincode: '560113', place: 'Bangalore', state: 'Karnataka' } as Address, location: { latitude: 12.9301487, longitude: 75.1242412 },authProviders: [{ provider: AuthProviders.Local, phash: 'tobecreated', userid: 'otherbt3@blocktech.dk' } as UserAuthProvider], verification: { activated: true, emailVerified: true, phoneVerified: true } as UserVerification, accounts: [{ accountId: 'QjYjsYmmuWPhYxt8hGjKx3cRH841rNv7w1', accountType: PaymentTypes.BTC } as CryptoAccount] } as User;
16 | cc | otherbt4@blocktech.dk | 9900318465 | Other4 | BT | 12.3487 | 77.7723 | Outskirts | Halli | Yelanka | Bangalore | Karnataka | India | 560114 |  |  | QjYjsYmmuWPhYxt8hGjKx3cRH841rNv7w3 |  |  |  | let user16 = { tenantId: 'cc', email: 'otherbt4@blocktech.dk', phone: '9900318465', language: Languages.US, role: RoleTypes.Standard, basic: { userId: 'otherbt4@blocktech.dk', firstName: 'Other4', lastName: 'BT', profilePhoto: 'other4_profile_photo', language: Languages.US.toString(), } as UserLite, address: { addressLine1: 'Outskirts', addressLine2: 'Halli', city: 'Yelanka', country: 'India', language: Languages.US, pincode: '560114', place: 'Bangalore', state: 'Karnataka' } as Address, location: { latitude: 12.3487, longitude: 77.77228 },authProviders: [{ provider: AuthProviders.Local, phash: 'tobecreated', userid: 'otherbt4@blocktech.dk' } as UserAuthProvider], verification: { activated: true, emailVerified: true, phoneVerified: true } as UserVerification, accounts: [{ accountId: 'QjYjsYmmuWPhYxt8hGjKx3cRH841rNv7w3', accountType: PaymentTypes.BTC } as CryptoAccount] } as User;

## seed.data.case
id | title | description | commission | amount | latitude | longitude | status | ratingCount | ratingOn | createdOn | publishedOn | completedOn | addressLine1 | addressLine2 | place | city | state | country | pincode | caseid_part | JSON
0001 | Please help to restore the village and their hope | Villagers have struggled through freezing cold in winter and threatening hurricanes in spring. They do not have capacity to bear the heavy rainfall and thunder in this monsoon and neither their weak shelter. | 0 | 1000 | 13.1186 | 77.5975 | Open | 3 | 2009-07-20T10:00:15 | 2009-06-20T10:00:10 | 2009-06-20T11:00:17 |  | Outskirts | Halli | Yelanka | Bangalore | Karnataka | India | 560099 | bangalore-case0001 | let c0001: Case = { tenantId: 'cc',caseId: 'bangalore-case0001', revision: 1, isagent: false, isactive: true,content: [{ lang: Languages.US.toString(), title: 'Please help to restore the village and their hope', description: 'Villagers have struggled through freezing cold in winter and threatening hurricanes in spring. They do not have capacity to bear the heavy rainfall and thunder in this monsoon and neither their weak shelter.' }],address: { addressLine1: 'Outskirts', addressLine2: 'Halli', city: 'Bangalore', country: 'India', language: Languages.US, pincode: '560099', place: 'Yelanka', state: 'Karnataka' } as Address, location: { latitude: 13.1186, longitude: 77.5975 },status: CaseStatus.Open, agentCommission: 0, baseCurrency: Currency.USD.toString(), amount: 1000,accountDetails: [ ], attachments: [ ], beneficiary: { } as UserLite,donations: [ ], rating: { count: 3, recentUpdate: new Date('2009-07-20T10:00:15'), average: 0 },createdOn:new Date('2009-06-20T10:00:10'),publishedOn: new Date('2009-06-20T11:00:17'),reportAbuse: { count: 0, recentUpdate: new Date() },category: [], tags: [] } as Case;
0002 | She Lost Her Parents to HIV, But She Wants An Education! | Rebecca is 16 years old and lives in Uganda. We share the same mum.Rebecca lost both her parents within the same year when she was 8 years. She have a family but no one is able to support her financially. A few weeks ago I went back to Uganda, the place I was born, and spent time with her. She is an amazing young woman whom wants to further her education despite of her financially sutuation and I am determined to make her wish come true. | 0 | 2000 | 28.7354 | 77.1638 | Open | 4 | 2009-07-20T10:00:16 | 2009-06-20T10:00:17 | 2009-07-20T10:00:17 |  | Bhalswa Lake | Town | Bhalswa Jahangir Pur | Delhi | New Delhi | India | 110033 | delhi-case0002 | let c0002: Case = { tenantId: 'cc',caseId: 'delhi-case0002', revision: 1, isagent: false, isactive: true,content: [{ lang: Languages.US.toString(), title: 'She Lost Her Parents to HIV, But She Wants An Education!', description: 'Rebecca is 16 years old and lives in Uganda. We share the same mum.Rebecca lost both her parents within the same year when she was 8 years. She have a family but no one is able to support her financially. A few weeks ago I went back to Uganda, the place I was born, and spent time with her. She is an amazing young woman whom wants to further her education despite of her financially sutuation and I am determined to make her wish come true.' }],address: { addressLine1: 'Bhalswa Lake', addressLine2: 'Town', city: 'Delhi', country: 'India', language: Languages.US, pincode: '110033', place: 'Bhalswa Jahangir Pur', state: 'New Delhi' } as Address, location: { latitude: 28.73542, longitude: 77.16383 },status: CaseStatus.Open, agentCommission: 0, baseCurrency: Currency.USD.toString(), amount: 2000,accountDetails: [ ], attachments: [ ], beneficiary: { } as UserLite,donations: [ ], rating: { count: 4, recentUpdate: new Date('2009-07-20T10:00:16'), average: 0 },createdOn:new Date('2009-06-20T10:00:17'),publishedOn: new Date('2009-07-20T10:00:17'),reportAbuse: { count: 0, recentUpdate: new Date() },category: [], tags: [] } as Case;
0003 | Feeding Children in Syria | My mission is to transport food,clothes and blankets to the children of the refugee camps in Syria. Every day I receive messages and photos from the camp with a desperate plea for help. So friends, followers, let us together make a way for them to get that help! These families are people who are living in a country destroyed by war. They do not wish to leave their home, but instead try and make it work in these refugee camps. Let us help them. I cannot make the war seize to an end, but I can transport food and comforting heat to them - with your help! | 0 | 1500 | 19.0402 | 72.85085 | Completed | 2 | 2009-07-20T10:00:17 | 2009-06-02T10:00:17 | 2009-06-20T10:20:17 | 2009-08-20T11:00:17 | Mahim railway station | Mahim | Dharavi | Mumbai | Maharashtra | India | 400017 | mumbai-case0003 | let c0003: Case = { tenantId: 'cc',caseId: 'mumbai-case0003', revision: 1, isagent: false, isactive: true,content: [{ lang: Languages.US.toString(), title: 'Feeding Children in Syria', description: 'My mission is to transport food,clothes and blankets to the children of the refugee camps in Syria. Every day I receive messages and photos from the camp with a desperate plea for help. So friends, followers, let us together make a way for them to get that help! These families are people who are living in a country destroyed by war. They do not wish to leave their home, but instead try and make it work in these refugee camps. Let us help them. I cannot make the war seize to an end, but I can transport food and comforting heat to them - with your help!' }],address: { addressLine1: 'Mahim railway station', addressLine2: 'Mahim', city: 'Mumbai', country: 'India', language: Languages.US, pincode: '400017', place: 'Dharavi', state: 'Maharashtra' } as Address, location: { latitude: 19.040208, longitude: 72.85085 },status: CaseStatus.Completed, agentCommission: 0, baseCurrency: Currency.USD.toString(), amount: 1500,accountDetails: [ ], attachments: [ ], beneficiary: { } as UserLite,donations: [ ], rating: { count: 2, recentUpdate: new Date('2009-07-20T10:00:17'), average: 0 },createdOn:new Date('2009-06-02T10:00:17'),publishedOn: new Date('2009-06-20T10:20:17'),completedOn:new Date('2009-08-20T11:00:17'),reportAbuse: { count: 0, recentUpdate: new Date() },category: [], tags: [] } as Case;
0004 | HyperLink HyperLink Social kitchen with refugees on Leros | Food is one of the most basic needs. Social living is also one basic need especially in times of life crisis. The aim of this case is to combine these two needs and create a social kitchen on Leros, where locals and refugees can cook abundant meals enough to cover refugees food needs, nourish them with home-made food and with the warmth of coexistence. The aim is therefore both practical, i.e. to provide food, but also social and psychological, i.e. create an opportunity for refugees, volunteers and locals to come together, share the joy of cooking and spread humaneness. There is also an aim of creating a cultural meeting, where both Middle-East and Greek food can be cooked. | 0 | 25000 | 17.3998 | 78.476615 | Open | 5 | 2009-07-20T10:00:18 | 2009-07-02T10:00:17 | 2009-07-02T10:30:17 |  | Near Lal Bahadur Shastri Stadium | Abids | Abids | Hyderabad | Telangana | India | 500004 | hyderabad-case0004 | let c0004: Case = { tenantId: 'cc',caseId: 'hyderabad-case0004', revision: 1, isagent: false, isactive: true,content: [{ lang: Languages.US.toString(), title: 'HyperLink HyperLink Social kitchen with refugees on Leros', description: 'Food is one of the most basic needs. Social living is also one basic need especially in times of life crisis. The aim of this case is to combine these two needs and create a social kitchen on Leros, where locals and refugees can cook abundant meals enough to cover refugees food needs, nourish them with home-made food and with the warmth of coexistence. The aim is therefore both practical, i.e. to provide food, but also social and psychological, i.e. create an opportunity for refugees, volunteers and locals to come together, share the joy of cooking and spread humaneness. There is also an aim of creating a cultural meeting, where both Middle-East and Greek food can be cooked.' }],address: { addressLine1: 'Near Lal Bahadur Shastri Stadium', addressLine2: 'Abids', city: 'Hyderabad', country: 'India', language: Languages.US, pincode: '500004', place: 'Abids', state: 'Telangana' } as Address, location: { latitude: 17.399782, longitude: 78.476615 },status: CaseStatus.Open, agentCommission: 0, baseCurrency: Currency.USD.toString(), amount: 25000,accountDetails: [ ], attachments: [ ], beneficiary: { } as UserLite,donations: [ ], rating: { count: 5, recentUpdate: new Date('2009-07-20T10:00:18'), average: 0 },createdOn:new Date('2009-07-02T10:00:17'),publishedOn: new Date('2009-07-02T10:30:17'),reportAbuse: { count: 0, recentUpdate: new Date() },category: [], tags: [] } as Case;
0005 | GIVE UP A NIGHT OUT TO SAVE A CHILDREN LIFE | Ebola had an insane impact around the world. You may think the crisis is over, but the disease has been a bomb in the lives of children who have become orphans overnight. To piece things back together for a group of amazing kids who have lost both of their parents to ebola, we are building a school / home to provide special and talented kids with a moral, social and traditional education in both technology and entrepreneurship. We are also using the space of the school to create a community and home environment to fuel family love. | 5 | 1500 | 13.0481 | 80.2214 | Completed | 0 | 2009-07-20T10:00:19 | 2009-07-20T11:00:17 | 2009-07-02T12:00:17 | 2019-08-15T11:00:17 | Kamarajapuram | Nungambakkam | Kodambakkam | Chennai | Tamil Nadu | India | 600034 | chennai-case0005 | let c0005: Case = { tenantId: 'cc',caseId: 'chennai-case0005', revision: 1, isagent: true, isactive: true,content: [{ lang: Languages.US.toString(), title: 'GIVE UP A NIGHT OUT TO SAVE A CHILDREN LIFE', description: 'Ebola had an insane impact around the world. You may think the crisis is over, but the disease has been a bomb in the lives of children who have become orphans overnight. To piece things back together for a group of amazing kids who have lost both of their parents to ebola, we are building a school / home to provide special and talented kids with a moral, social and traditional education in both technology and entrepreneurship. We are also using the space of the school to create a community and home environment to fuel family love.' }],address: { addressLine1: 'Kamarajapuram', addressLine2: 'Nungambakkam', city: 'Chennai', country: 'India', language: Languages.US, pincode: '600034', place: 'Kodambakkam', state: 'Tamil Nadu' } as Address, location: { latitude: 13.0481, longitude: 80.2214 },status: CaseStatus.Completed, agentCommission: 5, baseCurrency: Currency.USD.toString(), amount: 1500,accountDetails: [ ], attachments: [ ], beneficiary: { } as UserLite,donations: [ ], rating: { count: 0, recentUpdate: new Date('2009-07-20T10:00:19'), average: 0 },createdOn:new Date('2009-07-20T11:00:17'),publishedOn: new Date('2009-07-02T12:00:17'),completedOn:new Date('2019-08-15T11:00:17'),reportAbuse: { count: 0, recentUpdate: new Date() },category: [], tags: [] } as Case;
0006 | Gbowee Peace Foundation Africa | The organization envisions a peaceful, reconciled and empowered Africa that is responsible for investing in sustained individual and collective growth and development. Reflecting an institutional conviction – and international consensus – that peaceful, sustained development requires the meaningful participation and advancement of women and youth, the Foundation focuses its efforts on advancing the breadth of educational and leadership development opportunities for these key groups. A comprehensive scholarship program, youth empowerment activities and women gatherings comprise the Foundation’s core work. | 5 | 350 | 22.5958 | 88.2636 | Open | 3 | 2009-07-20T10:00:20 | 2009-07-20T12:00:17 | 2009-07-20T12:05:17 |  | Pilkhana | Howrah Station | Howrah | Kolkata | West Bengal | India | 711101 | kolkata-case0006 | let c0006: Case = { tenantId: 'cc',caseId: 'kolkata-case0006', revision: 1, isagent: true, isactive: true,content: [{ lang: Languages.US.toString(), title: 'Gbowee Peace Foundation Africa', description: 'The organization envisions a peaceful, reconciled and empowered Africa that is responsible for investing in sustained individual and collective growth and development. Reflecting an institutional conviction – and international consensus – that peaceful, sustained development requires the meaningful participation and advancement of women and youth, the Foundation focuses its efforts on advancing the breadth of educational and leadership development opportunities for these key groups. A comprehensive scholarship program, youth empowerment activities and women gatherings comprise the Foundation’s core work.' }],address: { addressLine1: 'Pilkhana', addressLine2: 'Howrah Station', city: 'Kolkata', country: 'India', language: Languages.US, pincode: '711101', place: 'Howrah', state: 'West Bengal' } as Address, location: { latitude: 22.5958, longitude: 88.2636 },status: CaseStatus.Open, agentCommission: 5, baseCurrency: Currency.USD.toString(), amount: 350,accountDetails: [ ], attachments: [ ], beneficiary: { } as UserLite,donations: [ ], rating: { count: 3, recentUpdate: new Date('2009-07-20T10:00:20'), average: 0 },createdOn:new Date('2009-07-20T12:00:17'),publishedOn: new Date('2009-07-20T12:05:17'),reportAbuse: { count: 0, recentUpdate: new Date() },category: [], tags: [] } as Case;
0007 | Kind Pickup For Refugees from Arrival to Departure. | We have rented a seven-person bus, that will enable us to transport the refugees coming into Lesbos on boats, from arrival gate at the seaport in Lesbos to the departure gate on the other end of the island, which on foot will take approximately. It is a long way to walk when you are hungry, tired and/or have a child or are a kid yourself. | 5 | 6000 | 20.4372 | 85.9119 | Completed | 2 | 2009-07-20T10:00:21 | 2009-07-20T13:00:17 | 2009-07-20T14:00:17 | 2019-08-10T11:00:17 | 561 & 562, Ekmara Vihar | Nayapalli | Salia Sahi | Bhubaneswar | Odisha | India | 751015 | bhubaneswar-case0007 | let c0007: Case = { tenantId: 'cc',caseId: 'bhubaneswar-case0007', revision: 1, isagent: true, isactive: true,content: [{ lang: Languages.US.toString(), title: 'Kind Pickup For Refugees from Arrival to Departure.', description: 'We have rented a seven-person bus, that will enable us to transport the refugees coming into Lesbos on boats, from arrival gate at the seaport in Lesbos to the departure gate on the other end of the island, which on foot will take approximately. It is a long way to walk when you are hungry, tired and/or have a child or are a kid yourself.' }],address: { addressLine1: '561 & 562, Ekmara Vihar', addressLine2: 'Nayapalli', city: 'Bhubaneswar', country: 'India', language: Languages.US, pincode: '751015', place: 'Salia Sahi', state: 'Odisha' } as Address, location: { latitude: 20.4372499, longitude: 85.911918 },status: CaseStatus.Completed, agentCommission: 5, baseCurrency: Currency.USD.toString(), amount: 6000,accountDetails: [ ], attachments: [ ], beneficiary: { } as UserLite,donations: [ ], rating: { count: 2, recentUpdate: new Date('2009-07-20T10:00:21'), average: 0 },createdOn:new Date('2009-07-20T13:00:17'),publishedOn: new Date('2009-07-20T14:00:17'),completedOn:new Date('2019-08-10T11:00:17'),reportAbuse: { count: 0, recentUpdate: new Date() },category: [], tags: [] } as Case;
0008 | Radha the receptionist, needs a computer. | Radha Anu is currently working as a receptionist for a private tourism company. However, she lately developed some health issues (thyroid disease) and cannot afford to go the office every day. She got an education in computer science at an evening college, and she sees that a computer would let her make a decent job as a computer consultant, where she could work from her bed to make a living for herself and her family. | 5 | 8000 | 19.0613 | 72.9258 | Open | 2 | 2009-07-20T10:00:22 | 2009-07-20T20:00:17 | 2009-07-21T10:00:17 |  | Shivaji Nagar | Govandi road | Baiganwadi | Mumbai | Maharashtra | India | 400023 | mumbai-case0008 | let c0008: Case = { tenantId: 'cc',caseId: 'mumbai-case0008', revision: 1, isagent: true, isactive: true,content: [{ lang: Languages.US.toString(), title: 'Radha the receptionist, needs a computer.', description: 'Radha Anu is currently working as a receptionist for a private tourism company. However, she lately developed some health issues (thyroid disease) and cannot afford to go the office every day. She got an education in computer science at an evening college, and she sees that a computer would let her make a decent job as a computer consultant, where she could work from her bed to make a living for herself and her family.' }],address: { addressLine1: 'Shivaji Nagar', addressLine2: 'Govandi road', city: 'Mumbai', country: 'India', language: Languages.US, pincode: '400023', place: 'Baiganwadi', state: 'Maharashtra' } as Address, location: { latitude: 19.0613, longitude: 72.9258 },status: CaseStatus.Open, agentCommission: 5, baseCurrency: Currency.USD.toString(), amount: 8000,accountDetails: [ ], attachments: [ ], beneficiary: { } as UserLite,donations: [ ], rating: { count: 2, recentUpdate: new Date('2009-07-20T10:00:22'), average: 0 },createdOn:new Date('2009-07-20T20:00:17'),publishedOn: new Date('2009-07-21T10:00:17'),reportAbuse: { count: 0, recentUpdate: new Date() },category: [], tags: [] } as Case;
0009 | Coconut Cart for Mr. Krishnappa. | Mr. Krishnappa is a modest man, making a modest living, working in Central-South Bangalore, Siddapura, as a roadside coconut vendor. He buys a the freshest and best looking coconuts, and snaps first the top part off, so his costumers can drink the highly nutritious coconut water with a straw, and then, when it is empty, he cracks it open and makes a natural spoon out of the coconut shell, so his costumers can enjoy the remaining natural coconut-meat. Mr. Krishnappa is supporting his family and that includes supplying food, shelter and paying for his wife medical bills, where he pays full prize as there is no compensation for economically challenged families, and his daughter and sons, whom are studying at college and needs their tuition and academic-related costs covered by Mr. Krishnappa. | 5 | 1000 | 13.1131 | 80.2886 | Open | 3 | 2009-07-20T10:00:23 | 2014-08-20T10:00:17 | 2014-08-20T10:04:17 |  | No: 25 and 26,Parrys Corner | Royapuram | Washermanpet | Chennai | Tamil Nadu | India | 600106 | chennai-case0009 | let c0009: Case = { tenantId: 'cc',caseId: 'chennai-case0009', revision: 1, isagent: true, isactive: true,content: [{ lang: Languages.US.toString(), title: 'Coconut Cart for Mr. Krishnappa.', description: 'Mr. Krishnappa is a modest man, making a modest living, working in Central-South Bangalore, Siddapura, as a roadside coconut vendor. He buys a the freshest and best looking coconuts, and snaps first the top part off, so his costumers can drink the highly nutritious coconut water with a straw, and then, when it is empty, he cracks it open and makes a natural spoon out of the coconut shell, so his costumers can enjoy the remaining natural coconut-meat. Mr. Krishnappa is supporting his family and that includes supplying food, shelter and paying for his wife medical bills, where he pays full prize as there is no compensation for economically challenged families, and his daughter and sons, whom are studying at college and needs their tuition and academic-related costs covered by Mr. Krishnappa.' }],address: { addressLine1: 'No: 25 and 26,Parrys Corner', addressLine2: 'Royapuram', city: 'Chennai', country: 'India', language: Languages.US, pincode: '600106', place: 'Washermanpet', state: 'Tamil Nadu' } as Address, location: { latitude: 13.1131, longitude: 80.2886 },status: CaseStatus.Open, agentCommission: 5, baseCurrency: Currency.USD.toString(), amount: 1000,accountDetails: [ ], attachments: [ ], beneficiary: { } as UserLite,donations: [ ], rating: { count: 3, recentUpdate: new Date('2009-07-20T10:00:23'), average: 0 },createdOn:new Date('2014-08-20T10:00:17'),publishedOn: new Date('2014-08-20T10:04:17'),reportAbuse: { count: 0, recentUpdate: new Date() },category: [], tags: [] } as Case;
0010 | Aiysha wants an education. Can you help? | Aiysha Rizwan is studying in the 10th grade and has high hopes to enter university level in India and make a good future for herself and help her family, who has helped her throughout her life. She lives with her father, Mr. Rizwan, who is a painter. Mr. Rizwan paints decoratively flowers on trucks and portraits of people, but is suffering from breathing problems and lung disease, because of toxic fumes, but cannot afford (due to living expenses and Aiysha tuition) to quit with a salary of INR 500 (USD $8) pr. day. Aiysha lives together with her mother, father and brother in a 8 sq. ft. x 9 sq. ft. shelter, which includes a small kitchen and an unhygienic restroom. | 10 | 1500 | 26.8997 | 75.7973 | Open | 0 | 2009-07-20T10:00:24 | 2009-11-20T10:00:17 | 2009-11-20T10:14:17 |  | Jyothi Nagar | Lalkothi | Kathputhli | Jaipur | Rajasthan | India | 302007 | jaipur-case0010 | let c0010: Case = { tenantId: 'cc',caseId: 'jaipur-case0010', revision: 1, isagent: true, isactive: true,content: [{ lang: Languages.US.toString(), title: 'Aiysha wants an education. Can you help?', description: 'Aiysha Rizwan is studying in the 10th grade and has high hopes to enter university level in India and make a good future for herself and help her family, who has helped her throughout her life. She lives with her father, Mr. Rizwan, who is a painter. Mr. Rizwan paints decoratively flowers on trucks and portraits of people, but is suffering from breathing problems and lung disease, because of toxic fumes, but cannot afford (due to living expenses and Aiysha tuition) to quit with a salary of INR 500 (USD $8) pr. day. Aiysha lives together with her mother, father and brother in a 8 sq. ft. x 9 sq. ft. shelter, which includes a small kitchen and an unhygienic restroom.' }],address: { addressLine1: 'Jyothi Nagar', addressLine2: 'Lalkothi', city: 'Jaipur', country: 'India', language: Languages.US, pincode: '302007', place: 'Kathputhli', state: 'Rajasthan' } as Address, location: { latitude: 26.8997, longitude: 75.7973 },status: CaseStatus.Open, agentCommission: 10, baseCurrency: Currency.USD.toString(), amount: 1500,accountDetails: [ ], attachments: [ ], beneficiary: { } as UserLite,donations: [ ], rating: { count: 0, recentUpdate: new Date('2009-07-20T10:00:24'), average: 0 },createdOn:new Date('2009-11-20T10:00:17'),publishedOn: new Date('2009-11-20T10:14:17'),reportAbuse: { count: 0, recentUpdate: new Date() },category: [], tags: [] } as Case;
0011 | Help for everyday life and for a Rickshaw Puller | Mr. Lakhminarayan is married to a woman named Lelavathi and lives in south Bangalore in Kurabarahalli, together with their two sons in a rented house. Before he became part of the fast paced Bangalore scene, Lakhminarayan worked hard at his fish retail business; but then he experienced a great loss in the business, and is today an Auto-Rickshaw driver. The Auto-Rickshaw is rented – and because he does not have ownership of his small cab-business, he has to give most of his earnings away to the owners and earns, after the cut, around Rs. 300 to Rs. 400, which is around $ 5 to 6 USD a day. To make him meet his ends, which includes some very basic necessities like his house rent, food for himself, his wife and his two kids, he is also very conscious about the necessity of an education for his two sons | 10 | 2500 | 17.7042 | 83.2978 | Open | 4 | 2009-07-20T10:00:25 | 2009-07-20T05:00:17 | 2009-07-20T10:00:17 |  | No: 20 and 24, Lower down road | Near Rythu bazzar | Pedagantyada | Visakhapatnam | Andhra Pradesh | India | 530044 | visakhapatnam-case0011 | let c0011: Case = { tenantId: 'cc',caseId: 'visakhapatnam-case0011', revision: 1, isagent: true, isactive: true,content: [{ lang: Languages.US.toString(), title: 'Help for everyday life and for a Rickshaw Puller', description: 'Mr. Lakhminarayan is married to a woman named Lelavathi and lives in south Bangalore in Kurabarahalli, together with their two sons in a rented house. Before he became part of the fast paced Bangalore scene, Lakhminarayan worked hard at his fish retail business; but then he experienced a great loss in the business, and is today an Auto-Rickshaw driver. The Auto-Rickshaw is rented – and because he does not have ownership of his small cab-business, he has to give most of his earnings away to the owners and earns, after the cut, around Rs. 300 to Rs. 400, which is around $ 5 to 6 USD a day. To make him meet his ends, which includes some very basic necessities like his house rent, food for himself, his wife and his two kids, he is also very conscious about the necessity of an education for his two sons' }],address: { addressLine1: 'No: 20 and 24, Lower down road', addressLine2: 'Near Rythu bazzar', city: 'Visakhapatnam', country: 'India', language: Languages.US, pincode: '530044', place: 'Pedagantyada', state: 'Andhra Pradesh' } as Address, location: { latitude: 17.704167, longitude: 83.297778 },status: CaseStatus.Open, agentCommission: 10, baseCurrency: Currency.USD.toString(), amount: 2500,accountDetails: [ ], attachments: [ ], beneficiary: { } as UserLite,donations: [ ], rating: { count: 4, recentUpdate: new Date('2009-07-20T10:00:25'), average: 0 },createdOn:new Date('2009-07-20T05:00:17'),publishedOn: new Date('2009-07-20T10:00:17'),reportAbuse: { count: 0, recentUpdate: new Date() },category: [], tags: [] } as Case;
0012 | Polio will not keep Iyaz from teaching and learning his pupils the computer. | Iyaz might have crippled legs as a result of suffering from Polio, but he is going as fast as he can to make his life as meaningful as possible. Iyaz was very fortunate to have a family whom supported him and helped him get the education that he, as well as everyone else, should get. He goes to University-level and has almost earned a degree in Commerce. He now has a wish to give his family – his mother, father, three brothers and two sisters – the support that he got and is still getting. Today he works as a part-time teacher along with his studies, to maintain the house needs with such a big family. | 10 | 8000 | 55.6761 | 12.5683 | Open | 5 | 2009-07-20T10:00:26 | 2009-07-20T00:00:17 | 2009-07-20T10:00:17 |  | Near Tivoli Gardens | Near Kongens Nytorv Station | Copenhagen | Copenhagen | Copenhagen | Denmark | 1051 | copenhagen-case0012 | let c0012: Case = { tenantId: 'cc',caseId: 'copenhagen-case0012', revision: 1, isagent: true, isactive: true,content: [{ lang: Languages.US.toString(), title: 'Polio will not keep Iyaz from teaching and learning his pupils the computer.', description: 'Iyaz might have crippled legs as a result of suffering from Polio, but he is going as fast as he can to make his life as meaningful as possible. Iyaz was very fortunate to have a family whom supported him and helped him get the education that he, as well as everyone else, should get. He goes to University-level and has almost earned a degree in Commerce. He now has a wish to give his family – his mother, father, three brothers and two sisters – the support that he got and is still getting. Today he works as a part-time teacher along with his studies, to maintain the house needs with such a big family.' }],address: { addressLine1: ' Near Tivoli Gardens', addressLine2: 'Near Kongens Nytorv Station', city: 'Copenhagen', country: 'Denmark', language: Languages.US, pincode: '1051', place: 'Copenhagen', state: 'Copenhagen' } as Address, location: { latitude: 55.676111, longitude: 12.568333 },status: CaseStatus.Open, agentCommission: 10, baseCurrency: Currency.USD.toString(), amount: 8000,accountDetails: [ ], attachments: [ ], beneficiary: { } as UserLite,donations: [ ], rating: { count: 5, recentUpdate: new Date('2009-07-20T10:00:26'), average: 0 },createdOn:new Date('2009-07-20T00:00:17'),publishedOn: new Date('2009-07-20T10:00:17'),reportAbuse: { count: 0, recentUpdate: new Date() },category: [], tags: [] } as Case;
0013 | Support to the children from Haku displaced by landslide | Around 990 households and the population of more than 4,000 were displaced from a small mountain of Haku. There were several landslides after earthquakes destructed houses claiming the life of nearly 100 people. 1.4% of the total population were killed by the disaster. They have now taking emergency shelter at camps located at different areas. Around 65 families are taking shelter in a camp at Kalikasthan. These people need zinc plate tins to build safer shelter and students need uniforms, school bags and some of the stationery and fees payable at school. There are 63 children studying at a nearby school temporarily. Total estimated cost for educational support is US $950. Total cost for total zinc plates (240 sheets) is US $2,000. | 10 | 9000 | 23.7583 | 90.3917 | Open | 2 | 2009-07-20T10:00:27 | 2009-07-20T02:00:17 | 2009-07-20T10:00:17 |  | Ward 37 | Tejgaon Thana | Begun Bari | Tejgaon | Dhaka | Bangladesh | 1215 | tejgaon-case0013 | let c0013: Case = { tenantId: 'cc',caseId: 'tejgaon-case0013', revision: 1, isagent: true, isactive: true,content: [{ lang: Languages.US.toString(), title: 'Support to the children from Haku displaced by landslide', description: 'Around 990 households and the population of more than 4,000 were displaced from a small mountain of Haku. There were several landslides after earthquakes destructed houses claiming the life of nearly 100 people. 1.4% of the total population were killed by the disaster. They have now taking emergency shelter at camps located at different areas. Around 65 families are taking shelter in a camp at Kalikasthan. These people need zinc plate tins to build safer shelter and students need uniforms, school bags and some of the stationery and fees payable at school. There are 63 children studying at a nearby school temporarily. Total estimated cost for educational support is US $950. Total cost for total zinc plates (240 sheets) is US $2,000.' }],address: { addressLine1: 'Ward 37', addressLine2: 'Tejgaon Thana', city: 'Tejgaon', country: 'Bangladesh', language: Languages.US, pincode: '1215', place: 'Begun Bari', state: 'Dhaka' } as Address, location: { latitude: 23.758333, longitude: 90.391667 },status: CaseStatus.Open, agentCommission: 10, baseCurrency: Currency.USD.toString(), amount: 9000,accountDetails: [ ], attachments: [ ], beneficiary: { } as UserLite,donations: [ ], rating: { count: 2, recentUpdate: new Date('2009-07-20T10:00:27'), average: 0 },createdOn:new Date('2009-07-20T02:00:17'),publishedOn: new Date('2009-07-20T10:00:17'),reportAbuse: { count: 0, recentUpdate: new Date() },category: [], tags: [] } as Case;
0014 | Transitional shelter in Nepal after earthquake | Most of you might already have heard about the recent earthquake that hit Nepal. Countless homes were destroyed and lives lost. The rebuilding effort is going to take years and a lot of effort. Kathmandu the capital was badly hit but the worse off were the villages around Kathmandu. A huge discrepancy exists between the city dwellers and the villagers in terms of wealth and resources. That is why I am putting together a team to help the villages around kathmandu put up transitional shelters. The concept of a transitional shelter (chapri in Nepali) is not new. All we are trying to do is initiate the building process and motivate them a bit. | 10 | 12000 | -37.8136 | 144.9631 | Completed | 3 | 2009-07-20T10:00:28 | 2018-07-20T10:00:17 | 2018-07-20T10:50:17 | 2019-08-20T11:00:17 | Stephen Stree | Little Lonsdale | Little Lon | Melbourne | Victoria | Austraila | 3005 | melbourne-case0014 | let c0014: Case = { tenantId: 'cc',caseId: 'melbourne-case0014', revision: 1, isagent: true, isactive: true,content: [{ lang: Languages.US.toString(), title: 'Transitional shelter in Nepal after earthquake', description: 'Most of you might already have heard about the recent earthquake that hit Nepal. Countless homes were destroyed and lives lost. The rebuilding effort is going to take years and a lot of effort. Kathmandu the capital was badly hit but the worse off were the villages around Kathmandu. A huge discrepancy exists between the city dwellers and the villagers in terms of wealth and resources. That is why I am putting together a team to help the villages around kathmandu put up transitional shelters. The concept of a transitional shelter (chapri in Nepali) is not new. All we are trying to do is initiate the building process and motivate them a bit.' }],address: { addressLine1: ' Stephen Stree', addressLine2: 'Little Lonsdale', city: 'Melbourne', country: 'Austraila', language: Languages.US, pincode: '3005', place: 'Little Lon', state: 'Victoria' } as Address, location: { latitude: -37.813611, longitude: 144.963056 },status: CaseStatus.Completed, agentCommission: 10, baseCurrency: Currency.USD.toString(), amount: 12000,accountDetails: [ ], attachments: [ ], beneficiary: { } as UserLite,donations: [ ], rating: { count: 3, recentUpdate: new Date('2009-07-20T10:00:28'), average: 0 },createdOn:new Date('2018-07-20T10:00:17'),publishedOn: new Date('2018-07-20T10:50:17'),completedOn:new Date('2019-08-20T11:00:17'),reportAbuse: { count: 0, recentUpdate: new Date() },category: [], tags: [] } as Case;
0015 | Help rebuild the village Khalte in Nepal | The village Khalte is located 1 hours drive from Katmandu (you can see the exact location on the map-link), and is accessible by a normal sedan cars if it is not raining. | 20 | 60000 | 35.8844 | 14.5069 | Open | 2 | 2009-07-20T10:00:29 | 2017-07-20T10:00:17 | 2017-07-20T11:00:17 |  | Outskirts | Halli | Manderaggio | Valletta | Malta | Malta | 409 | valletta-case0015 | let c0015: Case = { tenantId: 'cc',caseId: 'valletta-case0015', revision: 1, isagent: true, isactive: true,content: [{ lang: Languages.US.toString(), title: 'Help rebuild the village Khalte in Nepal', description: 'The village Khalte is located 1 hours drive from Katmandu (you can see the exact location on the map-link), and is accessible by a normal sedan cars if it is not raining.' }],address: { addressLine1: 'Outskirts', addressLine2: 'Halli', city: 'Valletta', country: 'Malta', language: Languages.US, pincode: '409', place: 'Manderaggio', state: 'Malta' } as Address, location: { latitude: 35.884444, longitude: 14.506944 },status: CaseStatus.Open, agentCommission: 20, baseCurrency: Currency.USD.toString(), amount: 60000,accountDetails: [ ], attachments: [ ], beneficiary: { } as UserLite,donations: [ ], rating: { count: 2, recentUpdate: new Date('2009-07-20T10:00:29'), average: 0 },createdOn:new Date('2017-07-20T10:00:17'),publishedOn: new Date('2017-07-20T11:00:17'),reportAbuse: { count: 0, recentUpdate: new Date() },category: [], tags: [] } as Case;
0016 | Lifeguards Vests Collected and Reused | We will get a serviceboat to collect the lifeguard vests, that lay around the coast from the refugees who had them on and then left them on the beach and transport them back to Turkey, for some one else to use for free. | 20 | 150000 | 26.8393 | 80.9231 | Open | 0 | 2009-07-20T10:00:30 | 2018-09-20T10:00:17 | 2018-09-21T10:00:17 |  | Vipin Khand 2 & 3 | Near Ambedkar Memorial Park | Gomti Nagar | Lucknow | Uttar Pradesh | India | 226010 | lucknow-case0016 | let c0016: Case = { tenantId: 'cc',caseId: 'lucknow-case0016', revision: 1, isagent: true, isactive: true,content: [{ lang: Languages.US.toString(), title: 'Lifeguards Vests Collected and Reused', description: 'We will get a serviceboat to collect the lifeguard vests, that lay around the coast from the refugees who had them on and then left them on the beach and transport them back to Turkey, for some one else to use for free.' }],address: { addressLine1: ' Vipin Khand 2 & 3', addressLine2: 'Near Ambedkar Memorial Park', city: 'Lucknow', country: 'India', language: Languages.US, pincode: '226010', place: 'Gomti Nagar', state: 'Uttar Pradesh' } as Address, location: { latitude: 26.839281, longitude: 80.923133 },status: CaseStatus.Open, agentCommission: 20, baseCurrency: Currency.USD.toString(), amount: 150000,accountDetails: [ ], attachments: [ ], beneficiary: { } as UserLite,donations: [ ], rating: { count: 0, recentUpdate: new Date('2009-07-20T10:00:30'), average: 0 },createdOn:new Date('2018-09-20T10:00:17'),publishedOn: new Date('2018-09-21T10:00:17'),reportAbuse: { count: 0, recentUpdate: new Date() },category: [], tags: [] } as Case;
0017 | Recycle of lifeguard vests and Fair Welcome help! | Some of the repercussions of the refugee-situation in Lesbos is that the beaches of Lesbos is littered with trash and discarded lifevests. We are going to make a plan for recycling lifeguard vests into a new product, made of refugees themselves. Cover-ups/carpets of pieces and mattresses made of the padded parts. This puts a strain on the Greek Lesbos community and on the environment as a whole and it needs to be dealt with. By purchasing garbage bags and rubber gloves etc. to enable us to hand picking trash from the beaches, with the help from locals like Lebsos hotel staff. | 20 | 5500 | 22.7177 | 75.8586 | Open | 0 | 2009-07-20T10:00:31 | 2009-07-20T10:00:17 | 2009-07-22T10:00:17 |  | Outskirts | Halli | Yelanka | Indore | Madhya Pradesh | India | 560115 | indore-case0017 | let c0017: Case = { tenantId: 'cc',caseId: 'indore-case0017', revision: 1, isagent: true, isactive: true,content: [{ lang: Languages.US.toString(), title: 'Recycle of lifeguard vests and Fair Welcome help!', description: 'Some of the repercussions of the refugee-situation in Lesbos is that the beaches of Lesbos is littered with trash and discarded lifevests. We are going to make a plan for recycling lifeguard vests into a new product, made of refugees themselves. Cover-ups/carpets of pieces and mattresses made of the padded parts. This puts a strain on the Greek Lesbos community and on the environment as a whole and it needs to be dealt with. By purchasing garbage bags and rubber gloves etc. to enable us to hand picking trash from the beaches, with the help from locals like Lebsos hotel staff.' }],address: { addressLine1: 'Outskirts', addressLine2: 'Halli', city: 'Indore', country: 'India', language: Languages.US, pincode: '560115', place: 'Yelanka', state: 'Madhya Pradesh' } as Address, location: { latitude: 22.717736, longitude: 75.85859 },status: CaseStatus.Open, agentCommission: 20, baseCurrency: Currency.USD.toString(), amount: 5500,accountDetails: [ ], attachments: [ ], beneficiary: { } as UserLite,donations: [ ], rating: { count: 0, recentUpdate: new Date('2009-07-20T10:00:31'), average: 0 },createdOn:new Date('2009-07-20T10:00:17'),publishedOn: new Date('2009-07-22T10:00:17'),reportAbuse: { count: 0, recentUpdate: new Date() },category: [], tags: [] } as Case;
0018 | Change lives by supporting local leaders | Part of a comprehensive water, sanitation, and hygiene (WASH) program includes the development of regular hand-washing practices. In many communities, tippy tap stands are installed and used to make this possible. A tippy tap is a hanging jug that is filled with and tipped to dispense clean water, with soap kept nearby. Typically, this was the solution that was used in North Kamagambo as well. | 20 | 15000 | 55.6797 | 12.5906 | Open | 0 | 2009-07-20T10:00:32 | 2009-07-17T10:00:17 | 2009-07-20T16:00:17 |  | No: 219, Along side Nyhavn Canal | Near Kongens Nytorv station | Nyhavn | Copenhagen | Copenhagen | Denmark | 1051 | copenhagen-case0018 | let c0018: Case = { tenantId: 'cc',caseId: 'copenhagen-case0018', revision: 1, isagent: true, isactive: true,content: [{ lang: Languages.US.toString(), title: 'Change lives by supporting local leaders', description: 'Part of a comprehensive water, sanitation, and hygiene (WASH) program includes the development of regular hand-washing practices. In many communities, tippy tap stands are installed and used to make this possible. A tippy tap is a hanging jug that is filled with and tipped to dispense clean water, with soap kept nearby. Typically, this was the solution that was used in North Kamagambo as well.' }],address: { addressLine1: 'No: 219, Along side Nyhavn Canal', addressLine2: 'Near Kongens Nytorv station', city: 'Copenhagen', country: 'Denmark', language: Languages.US, pincode: '1051', place: 'Nyhavn', state: 'Copenhagen' } as Address, location: { latitude: 55.679722, longitude: 12.590556 },status: CaseStatus.Open, agentCommission: 20, baseCurrency: Currency.USD.toString(), amount: 15000,accountDetails: [ ], attachments: [ ], beneficiary: { } as UserLite,donations: [ ], rating: { count: 0, recentUpdate: new Date('2009-07-20T10:00:32'), average: 0 },createdOn:new Date('2009-07-17T10:00:17'),publishedOn: new Date('2009-07-20T16:00:17'),reportAbuse: { count: 0, recentUpdate: new Date() },category: [], tags: [] } as Case;
0019 | Building a nation fit for children | World Vision India works in 123 districts impacting around 26 lakh children and their families in over 6200 communities spread across 24 states and the National Capital Region to address issues affecting children in partnership with governments, civil societies, donors and corporates. With you, we can build a nation fit for children. Join us. Together for children. For change. For life. | 20 | 18000 | 25.6 | 85.1 | Open | 2 | 2009-07-20T10:00:33 | 2009-07-01T10:00:17 | 2009-07-01T17:00:17 |  | Outskirts | Village | Bihar old city | Patna | Bihar | India | 800005 | patna-case0019 | let c0019: Case = { tenantId: 'cc',caseId: 'patna-case0019', revision: 1, isagent: true, isactive: true,content: [{ lang: Languages.US.toString(), title: 'Building a nation fit for children', description: 'World Vision India works in 123 districts impacting around 26 lakh children and their families in over 6200 communities spread across 24 states and the National Capital Region to address issues affecting children in partnership with governments, civil societies, donors and corporates. With you, we can build a nation fit for children. Join us. Together for children. For change. For life.' }],address: { addressLine1: 'Outskirts', addressLine2: 'Village ', city: 'Patna', country: 'India', language: Languages.US, pincode: '800005', place: 'Bihar old city', state: 'Bihar' } as Address, location: { latitude: 25.6, longitude: 85.1 },status: CaseStatus.Open, agentCommission: 20, baseCurrency: Currency.USD.toString(), amount: 18000,accountDetails: [ ], attachments: [ ], beneficiary: { } as UserLite,donations: [ ], rating: { count: 2, recentUpdate: new Date('2009-07-20T10:00:33'), average: 0 },createdOn:new Date('2009-07-01T10:00:17'),publishedOn: new Date('2009-07-01T17:00:17'),reportAbuse: { count: 0, recentUpdate: new Date() },category: [], tags: [] } as Case;
0020 | Child Sponsorship | Child sponsorship is one of the best ways to give children better lives and futures. Sponsoring a child through World Vision India is one of the most effective, inspiring and rewarding ways to help children. You will be doing much more than helping to meet children basic needs – you will be helping to equip them for life. By bringing about lasting change in your sponsored child community, you will also be improving the lives of many other vulnerable children. When you sponsor a child, you will receive photograph of your sponsored child, information about your child, child family and community, annual report indicating the progress of your child, World Vision India’s magazine Jeevan Sparsh and an opportunity to gift, write or visit your sponsored child. | 6 | 22000 | 11.0055 | 76.9661 | Open | 3 | 2009-07-20T10:00:34 | 2009-07-20T10:00:17 | 2009-07-20T19:00:17 |  | Near National Textiles Ltd | Beside chruch | Anupparpalayam | Coimbatore | Tamil Nadu | India | 641009 | coimbatore-case0020 | let c0020: Case = { tenantId: 'cc',caseId: 'coimbatore-case0020', revision: 1, isagent: true, isactive: true,content: [{ lang: Languages.US.toString(), title: 'Child Sponsorship', description: 'Child sponsorship is one of the best ways to give children better lives and futures. Sponsoring a child through World Vision India is one of the most effective, inspiring and rewarding ways to help children. You will be doing much more than helping to meet children basic needs – you will be helping to equip them for life. By bringing about lasting change in your sponsored child community, you will also be improving the lives of many other vulnerable children. When you sponsor a child, you will receive photograph of your sponsored child, information about your child, child family and community, annual report indicating the progress of your child, World Vision India’s magazine Jeevan Sparsh and an opportunity to gift, write or visit your sponsored child.' }],address: { addressLine1: 'Near National Textiles Ltd', addressLine2: 'Beside chruch', city: 'Coimbatore', country: 'India', language: Languages.US, pincode: '641009', place: 'Anupparpalayam', state: 'Tamil Nadu' } as Address, location: { latitude: 11.005547, longitude: 76.966122 },status: CaseStatus.Open, agentCommission: 6, baseCurrency: Currency.USD.toString(), amount: 22000,accountDetails: [ ], attachments: [ ], beneficiary: { } as UserLite,donations: [ ], rating: { count: 3, recentUpdate: new Date('2009-07-20T10:00:34'), average: 0 },createdOn:new Date('2009-07-20T10:00:17'),publishedOn: new Date('2009-07-20T19:00:17'),reportAbuse: { count: 0, recentUpdate: new Date() },category: [], tags: [] } as Case;
0021 | World vision need help | World Vision India is a Christian organisation working to create a positive and enduring change in the lives of children, families and communities living in abject poverty and undue inequality. Irrespective of religion, caste, creed, race, ethnicity or gender, World Vision extends a helping hand to anyone and everyone who deserve it. With a wide network spanning 174 locations in India, World Vision lends help through long-term sustainable community programs and immediate disaster relief assistance. | 6 | 25000 | 17.9784 | 79.6002 | Draft | 0 |  | 2009-07-03T10:00:17 |  |  | Outskirts | Halli | Brahmanawada | Warangal | Telangana | India | 506011 | warangal-case0021 | let c0021: Case = { tenantId: 'cc',caseId: 'warangal-case0021', revision: 1, isagent: true, isactive: true,content: [{ lang: Languages.US.toString(), title: 'World vision need help', description: 'World Vision India is a Christian organisation working to create a positive and enduring change in the lives of children, families and communities living in abject poverty and undue inequality. Irrespective of religion, caste, creed, race, ethnicity or gender, World Vision extends a helping hand to anyone and everyone who deserve it. With a wide network spanning 174 locations in India, World Vision lends help through long-term sustainable community programs and immediate disaster relief assistance.' }],address: { addressLine1: 'Outskirts', addressLine2: 'Halli', city: 'Warangal', country: 'India', language: Languages.US, pincode: '506011', place: 'Brahmanawada', state: 'Telangana' } as Address, location: { latitude: 17.978423, longitude: 79.600209 },status: CaseStatus.Draft, agentCommission: 6, baseCurrency: Currency.USD.toString(), amount: 25000,accountDetails: [ ], attachments: [ ], beneficiary: { } as UserLite,donations: [ ], rating: { count: 0, recentUpdate: new Date(''), average: 0 },createdOn:new Date('2009-07-03T10:00:17'),reportAbuse: { count: 0, recentUpdate: new Date() },category: [], tags: [] } as Case;
0022 | Money brings clean water to people in need | Support one of our many fundraisers raising money for clean water. Give monthly, and you will become a part of The Spring, a passionate community invested in a world where everyone has clean water. | 6 | 33000 | 23.3478 | 85.3386 | Draft | 0 |  | 2009-07-04T10:00:17 |  |  | Gurudwara road | Bhawani Pur Site | Bokaro Steel City | Ranchi | Jharkhand | India | 560120 | ranchi-case0022 | let c0022: Case = { tenantId: 'cc',caseId: 'ranchi-case0022', revision: 1, isagent: true, isactive: true,content: [{ lang: Languages.US.toString(), title: 'Money brings clean water to people in need', description: 'Support one of our many fundraisers raising money for clean water. Give monthly, and you will become a part of The Spring, a passionate community invested in a world where everyone has clean water.' }],address: { addressLine1: 'Gurudwara road', addressLine2: 'Bhawani Pur Site', city: 'Ranchi', country: 'India', language: Languages.US, pincode: '560120', place: 'Bokaro Steel City', state: 'Jharkhand' } as Address, location: { latitude: 23.347768, longitude: 85.338564 },status: CaseStatus.Draft, agentCommission: 6, baseCurrency: Currency.USD.toString(), amount: 33000,accountDetails: [ ], attachments: [ ], beneficiary: { } as UserLite,donations: [ ], rating: { count: 0, recentUpdate: new Date(''), average: 0 },createdOn:new Date('2009-07-04T10:00:17'),reportAbuse: { count: 0, recentUpdate: new Date() },category: [], tags: [] } as Case;
0023 | Donate for flood victims | The water level in flood-hit Kerala has started to recede, but rebuilding the southern Indian state could take years. After all, the calamity, the worst Kerala has seen in a century, has displaced over a million people who are currently staying at relief camps. As the rains ease, the focus will be on aiding those whose houses and livelihoods were destroyed, a scale of rebuilding which will require billions of dollars. | 6 | 45000 | 26.2684 | 73.0059 | Draft | 0 |  | 2009-06-20T10:00:17 |  |  | RJ SH16 | Near Khariya Market | New Roop Nagar | Jodhpur | Rajasthan | India | 342006 | jodhpur-case0023 | let c0023: Case = { tenantId: 'cc',caseId: 'jodhpur-case0023', revision: 1, isagent: true, isactive: true,content: [{ lang: Languages.US.toString(), title: 'Donate for flood victims', description: 'The water level in flood-hit Kerala has started to recede, but rebuilding the southern Indian state could take years. After all, the calamity, the worst Kerala has seen in a century, has displaced over a million people who are currently staying at relief camps. As the rains ease, the focus will be on aiding those whose houses and livelihoods were destroyed, a scale of rebuilding which will require billions of dollars.' }],address: { addressLine1: 'RJ SH16', addressLine2: 'Near Khariya Market', city: 'Jodhpur', country: 'India', language: Languages.US, pincode: '342006', place: 'New Roop Nagar', state: 'Rajasthan' } as Address, location: { latitude: 26.26841, longitude: 73.005943 },status: CaseStatus.Draft, agentCommission: 6, baseCurrency: Currency.USD.toString(), amount: 45000,accountDetails: [ ], attachments: [ ], beneficiary: { } as UserLite,donations: [ ], rating: { count: 0, recentUpdate: new Date(''), average: 0 },createdOn:new Date('2009-06-20T10:00:17'),reportAbuse: { count: 0, recentUpdate: new Date() },category: [], tags: [] } as Case;
0024 | case 24 | case 24 description | 6 | 65000 | 26.1761 | 91.7629 | Obsolete | 0 | 2009-07-20T10:00:38 | 2009-04-20T10:00:17 |  |  | Near 4th Assam Police station | Santi Nagar | Kahilipara | Guwāhāti | Assam | India | 560122 | guwāhāti-case0024 | let c0024: Case = { tenantId: 'cc',caseId: 'guwāhāti-case0024', revision: 1, isagent: true, isactive: true,content: [{ lang: Languages.US.toString(), title: 'case 24', description: 'case 24 description' }],address: { addressLine1: 'Near 4th Assam Police station', addressLine2: 'Santi Nagar', city: 'Guwāhāti', country: 'India', language: Languages.US, pincode: '560122', place: 'Kahilipara', state: 'Assam' } as Address, location: { latitude: 26.176076, longitude: 91.762932 },status: CaseStatus.Obsolete, agentCommission: 6, baseCurrency: Currency.USD.toString(), amount: 65000,accountDetails: [ ], attachments: [ ], beneficiary: { } as UserLite,donations: [ ], rating: { count: 0, recentUpdate: new Date('2009-07-20T10:00:38'), average: 0 },createdOn:new Date('2009-04-20T10:00:17'),reportAbuse: { count: 0, recentUpdate: new Date() },category: [], tags: [] } as Case;
0025 | case 25 | case 25 description | 0 | 17000 | 30.7363 | 76.7884 | Obsolete | 0 | 2009-07-20T10:00:39 | 2009-05-20T10:00:17 |  |  | 17H, 17th Sector | Near Rose Garden | Chandigarh Housing Board | Chandigarh | Chandigarh | India | 560123 | chandigarh-case0025 | let c0025: Case = { tenantId: 'cc',caseId: 'chandigarh-case0025', revision: 1, isagent: false, isactive: true,content: [{ lang: Languages.US.toString(), title: 'case 25', description: 'case 25 description' }],address: { addressLine1: '17H, 17th Sector', addressLine2: 'Near Rose Garden', city: 'Chandigarh', country: 'India', language: Languages.US, pincode: '560123', place: 'Chandigarh Housing Board', state: 'Chandigarh' } as Address, location: { latitude: 30.736292, longitude: 76.788398 },status: CaseStatus.Obsolete, agentCommission: 0, baseCurrency: Currency.USD.toString(), amount: 17000,accountDetails: [ ], attachments: [ ], beneficiary: { } as UserLite,donations: [ ], rating: { count: 0, recentUpdate: new Date('2009-07-20T10:00:39'), average: 0 },createdOn:new Date('2009-05-20T10:00:17'),reportAbuse: { count: 0, recentUpdate: new Date() },category: [], tags: [] } as Case;
paymentTypes: [PaymentTypes.BTC, PaymentTypes.BankDirect],,

## VSTS_ValidationWS_1 (hidden)
value doesn't matter | value doesn't matter | value doesn't matter | value doesn't matter | \ | \ | Approved | Select User... | Done | Select User... | Done | Approved | Select User... | Select User... | Closed | Select User... | Approved | Select User... | Done | Select User... | Closed | Select User... | Approved | Select User... | Bug
readOnlyTestRange_@ | readOnlyTestRange_0 | readOnlyTestRange_M/d/yyyy h:mm AM/PM | readOnlyTestRange_General | all_VSTS_16a157f1_5ad2_409b_ab0b_273ecc0adfe9_System.AreaPath | \Sprint 1 | Committed | Administrator | In Progress | Administrator | In Progress | Committed | Administrator | Administrator | Open | Administrator | Committed | Administrator | In Progress | Administrator | Design | Administrator | Committed | Administrator | Epic
[5 empty] | \Sprint 2 | Done | Atul Kandyong | New | Atul Kandyong | New | Done | Atul Kandyong | Atul Kandyong | all_VSTS_16a157f1_5ad2_409b_ab0b_273ecc0adfe9_Impediment_System.State | Atul Kandyong | Done | Atul Kandyong | Removed | Atul Kandyong | Ready | Atul Kandyong | Done | Atul Kandyong | Feature
[5 empty] | \Sprint 3 | New | Omkar Sai Sunku | Removed | Omkar Sai Sunku | Removed | New | Omkar Sai Sunku | Omkar Sai Sunku |  | Omkar Sai Sunku | New | Omkar Sai Sunku | To Do | Omkar Sai Sunku | all_VSTS_16a157f1_5ad2_409b_ab0b_273ecc0adfe9_Test Case_System.State | Omkar Sai Sunku | New | Omkar Sai Sunku | Impediment
[5 empty] | \Sprint 4 | Removed | Pavan Kulkarni | all_VSTS_16a157f1_5ad2_409b_ab0b_273ecc0adfe9_Epic_System.State | Pavan Kulkarni | all_VSTS_16a157f1_5ad2_409b_ab0b_273ecc0adfe9_Feature_System.State | Removed | Pavan Kulkarni | Pavan Kulkarni |  | Pavan Kulkarni | Removed | Pavan Kulkarni | all_VSTS_16a157f1_5ad2_409b_ab0b_273ecc0adfe9_Task_System.State | Pavan Kulkarni |  | Pavan Kulkarni | Removed | Pavan Kulkarni | Product Backlog Item
[5 empty] | \Sprint 5 | all_VSTS_16a157f1_5ad2_409b_ab0b_273ecc0adfe9_Bug_System.State | Shiju Madamchery |  | Shiju Madamchery |  | VSTS_16a157f1_5ad2_409b_ab0b_273ecc0adfe9_FC-70-5F-3C-24-90-2F-CA-47-22-34-91-99-86-B3-1A-2D-B3-FF-2F | Shiju Madamchery | Shiju Madamchery |  | Shiju Madamchery | all_VSTS_16a157f1_5ad2_409b_ab0b_273ecc0adfe9_Product Backlog Item_System.State | Shiju Madamchery |  | Shiju Madamchery |  | Shiju Madamchery | In Progress | Shiju Madamchery | Task
[5 empty] | \Sprint 6 |  | Tarun Kumar Upadhyaya |  | Tarun Kumar Upadhyaya |  |  | Tarun Kumar Upadhyaya | Tarun Kumar Upadhyaya |  | Tarun Kumar Upadhyaya |  | Tarun Kumar Upadhyaya |  | Tarun Kumar Upadhyaya |  | Tarun Kumar Upadhyaya | Closed | Tarun Kumar Upadhyaya | Test Case
[5 empty] | all_VSTS_16a157f1_5ad2_409b_ab0b_273ecc0adfe9_System.IterationPath |  | Thorkild Grothe Moller |  | Thorkild Grothe Moller |  |  | Thorkild Grothe Moller | Thorkild Grothe Moller |  | Thorkild Grothe Moller |  | Thorkild Grothe Moller |  | Thorkild Grothe Moller |  | Thorkild Grothe Moller | Open | Thorkild Grothe Moller | all_VSTS_16a157f1_5ad2_409b_ab0b_273ecc0adfe9_System.WorkItemType
[7 empty] | all_VSTS_16a157f1_5ad2_409b_ab0b_273ecc0adfe9_Bug_System.AssignedTo |  | all_VSTS_16a157f1_5ad2_409b_ab0b_273ecc0adfe9_Epic_System.AssignedTo |  |  | VSTS_16a157f1_5ad2_409b_ab0b_273ecc0adfe9_42-0D-57-2A-22-A1-21-F3-1A-CF-8E-48-A1-D5-26-11-35-67-A1-12 | all_VSTS_16a157f1_5ad2_409b_ab0b_273ecc0adfe9_Feature_System.AssignedTo |  | all_VSTS_16a157f1_5ad2_409b_ab0b_273ecc0adfe9_Impediment_System.AssignedTo |  | all_VSTS_16a157f1_5ad2_409b_ab0b_273ecc0adfe9_Product Backlog Item_System.AssignedTo |  | all_VSTS_16a157f1_5ad2_409b_ab0b_273ecc0adfe9_Task_System.AssignedTo |  | all_VSTS_16a157f1_5ad2_409b_ab0b_273ecc0adfe9_Test Case_System.AssignedTo | To Do | all_VSTS_16a157f1_5ad2_409b_ab0b_273ecc0adfe9_System.AssignedTo
Design
Ready
all_VSTS_16a157f1_5ad2_409b_ab0b_273ecc0adfe9_System.State