## Epic and Sprints
Common Collection |  |  |  | Completed
| Pre sprint activities - CC Foundation |  | Sprint 0 |  | 74.44%
| Framework |  |  |  | 67.5%
| Base Service framework - service |  |  | 70%
| Mongo - DAL (mongoose) |  |  | 70%
| BLL - Access DAL (nodejs) |  |  | 80%
| Service API - (expressjs) |  |  | 80%
| Angular basic components |  |  | 80%
| Globalisation - client app |  |  | 60%
| Globalisation - service |  |  | 60%
| Email - handling |  |  | 40%
| RnD/POC/Prototype |  |  |  | 40%
| File handling - RnD |  |  | 50%
| Payment integration - RnD |  |  | 30%
| Auth |  |  |  | 90%
| Auth - Login |  |  | 90%
| Auth - Thirdparty login Facebook |  |  | 90%
| Auth - Thirdparty login Goolge |  |  | 90%
| Auth - Register |  |  | 90%
| Auth - Activate |  |  | 90%
| Auth - View profile |  |  | 90%
| Auth - Change Password |  |  | 90%
| Auth - Forgot Password |  |  | 90%
Sprints
TFS ID | Title 1 | Priority | Effort (Storypoint)
27 | As a visitor, I must be able to view list of published cases on home page. | 1 | 5 | 0% | Sprint 1: JUL 24 - AUG 5
53 | View list of cases - Injest cases and supporting data back end | 2 | 2 | 0%
41 | As a visitor, I must be able to view list of published cases on home page. | 2 | 3 | 0%
28 | As a visitor, I must be able to view list of published cases on home page sorted by recent and top rated and paginated. | 1 | 2 | 0%
43 | View list of cases - Injest cases and supporting data back end | 2 | 2 | 0%
9 | As visitor, I must be able to view details of a case. | 2 | 3 | 0%
44 | As visitor, I must be able to view details of a case. | 2 | 3 | 0%
54 | As visitor, I must be able to view photos in case details view. | 2 | 2 | 0%
55 | As visitor, I must be able to view photos in case details view. | 2 | 2 | 0%
15 | As a visitor, I must be able to view average rating of a case. | 2 | 2 | 0%
49 | As a visitor, I must be able to view average rating of a case. | 2 | 2 | 0% |  | Sprint 2: AUG 7 - AUG 20
29 | As a visitor, I must be able to view list of donors for a particular case. | 2 | 3 | 0%
47 | As a visitor, I must be able to view list of donors for a particular case. | 2 | 3 | 0%
18 | As a visitor, I must be able to view rating history and description for a case. | 2 | 3 | 0%
51 | As a visitor, I must be able to view rating history and description. | 2 | 3 | 0%
30 | As a visitor, I must be able to view list of donors for a particular case sorted by donation amount. | 2 | 1 | 0%
48 | As a visitor, I must be able to view list of donors for a particular case sorted by donation amount. | 2 | 1 | 0%
34 | As a visitor, I must be able to view Beneficiary profile for a case. | 2 | 3 | 0%
45 | As a visitor, I must be able to view Beneficiary profile for a case. | 2 | 3 | 0%
35 | As a visitor, I must be able to view Benefactor/Donor profile for a case. | 2 | 3 | 0%
46 | As a visitor, I must be able to view Benefactor/Donor profile for a case. | 2 | 3 | 0%
36 | As a visitor, I must be able to view average rating of a Beneficiary. | 2 | 2 | 0%
50 | As a visitor, I must be able to view average rating of a Beneficiary. | 2 | 2 | 0%
39 | As a visitor, I must be able to view rating history and description for a beneficiary. | 2 | 3 | 0%
52 | As a visitor, I must be able to view rating history and description. | 2 | 3 | 0%
16 | As a registered user, I must be able to rate a case along with description. | 3 | 2 | 0%
37 | As a registered user, I must be able to rate a beneficiary along with description. | 3 | 2 | 0%
17 | As a registered user, I must be able to override my rating and rating description. | 3 | 1 | 0% |  |  | Sprint 3: AUG 21 - SEP 3
38 | As a registered user, I must be able to override my rating and rating description for a beneficiary. | 3 | 1 | 0%
3 | As Beneficiary, I must be able to list down my cases created by me. | 3 | 2 | 0%
40 | As a benefactor/donor, I must be able to list down cases which I have donated | 3 | 2 | 0%
4 | As Beneficiary, I must be able to detailed view case created by me. | 3 | 2 | 0%
1 | As Beneficiary, I must be able to create a case | 3 | 2 | 0%
2 | As Beneficiary, I must be able to edit a case | 3 | 2 | 0%
5 | As Beneficiary, I must be able to mark my case as Published. | 3 | 1 | 0% |  |  |  | Sprint 4: SEP 4 - SEP 17
7 | As Beneficiary, I must be able to edit only case which is in Draft. | 3 | 1 | 0%
22 | As a Beneficiary, I must be able to provide geo location while creating a case. | 3 | 1 | 0%
24 | As a Beneficiary, I must be able to upload photos of a case. | 3 | 3 | 0%
25 | As a Beneficiary, I must be able to rearrange photos uploaded. | 3 | 2 | 0%
26 | As a Beneficiary, I must be able to set a photo as primary. | 3 | 1 | 0%
6 | As Beneficiary, I must be able to mark my case as Obsolete. | 4 | 1 | 0%
8 | As Beneficiary, I must be able to preview a case. | 4 | 3 | 0% |  |  |  |  | Sprint 5: SEP 18 - OCT 1
14 | As visitor, I must be able to view and provide comments for a case by FB credentials. | 4 | 2 | 0%
19 | As a registered user, I must be able to report a case as not genuine/abuse. | 4 | 2 | 0%
20 | As a visitor, I must be able to Like and/or share a case on Facebook. | 4 | 2 | 0%
21 | As a visitor, I must be able to Like and/or share a case on Instagram. | 4 | 2 | 0%
23 | As a Beneficiary, I must be able to set and adjust geo location from map based on the address while creating a case so that it will be displayed in case page while viewing or previewing. | 4 | 3 | 0%
31 | As a beneficiary, I must be able to provide my story which will be displayed to the site visitors on public profile. | 4 | 1 | 0%
32 | As a benefactor, I must be able to provide social media links which will be displayed to site visotors on public profile. | 4 | 1 | 0%
33 | As a benefactor, I must be able to provide 'loan reason' which will be displayed to site visotors on public profile. | 4 | 1 | 0%
| Payment Integration and CC Final steps | [8 empty] | OCT 1 - OCT 29
Testing and Release
Customer Support
Payment Integration - Bitcoin
Payment Integration - Other digital currencies
Administration - View Transactions
Payment Integration - Direct Bank
Payment Integration - CC
Administration - KYC Handling
| Production - Stabilisation Testing and Release |  |  |  | 2 Weeks - Oct 31 - Nov 12

## Sprint01
Tarun - Scrum Master | Sprint 01
| 2019-07-24 | 2019-07-25 | 2019-07-26 | 2019-07-27 | 2019-07-28 | 2019-07-29 | 2019-07-30 | 2019-07-31 | 2019-08-01 | 2019-08-02 | 2019-08-03 | 2019-08-04 | 2019-08-05 | 2019-08-06 | Bandwidth
Athul | [14 empty] | 80 | bar: 2019-07-24 to 2019-08-06
Pavan | 1 | 1 | 0.5 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 76
Om | 1 | 1 | 1 |  |  | 1 | 1 | 1 | Leave | Leave |  |  | 1 | 1 | 64
Shiju | 1 | 1 | 1 |  |  | Leave | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 72
292
View list of cases - Injest cases and supporting data back end | bar: 2019-07-26
As a visitor, I must be able to view list of published cases on home page. | bar: 2019-07-31
As a visitor, I must be able to view list of published cases on home page sorted by recent and top rated and paginated. | bar: 2019-08-02
As visitor, I must be able to view details of a case. | bar: 2019-07-29
As a visitor, I must be able to view Beneficiary profile for a case. | bar: 2019-08-01
As a visitor, I must be able to view Benefactor/Donor profile for a case. | bar: 2019-08-04
As a visitor, I must be able to view list of donors for a particular case. | bar: 2019-08-05
As a visitor, I must be able to view list of donors for a particular case sorted by donation amount.. | bar: 2019-08-05
Sprint planning meeting | 2019-07-24: 2019-07-24
| 10:00 | 11:00
Fill details in userstory/feature
Assignment
Delivery plan

## Epics
SlNo | Epics | Userstories | Description | Column4 | Priority | Size (S, M, L, XL) | Description/ Dependancy | Sprint (Relative) | Column1 | Sprints | Column2 | Column3
1 | Case Management (project) |  |  |  | 0
1.01 |  | Create/modify a project/case | add/edit: title, description, amount, currency, commission. |  |  | 3 |  |  | Commission setup, title, description, associated beneficiary |  | 1
|  | List and View a case - for beneficiary | my cases: title, photo, total donated - view, edit (no pagination,no file upload, only bind the link rom DB) view: title, photo, summary, total donated, amount. Commission | As Beneficiary, I must be able to list down my cases created by me. As Beneficiary, I must be able to detailed view case created by me. |  | 3
1.02 |  | Workflow - Draft => Publish => Maturity => Closed => Obsolete (TBD) | Draft - Edit, Publish - Readonly, Closed - Readonly, Obsolete - Admin/owner make it obsolete. Created case will initially mark as draft and draft case can be edited by the ower. Ownere will be able to publithe case when it is in draft state. Once case id published state, the case will be come readonly. Ownere will be abele to mark it as obsolete when the case is in Draft and/or Published. Published/Obsolete will make case as readonly. | As Beneficiary, I must be able to mark my case as Published. As Beneficiary, I must be able to mark my case as Obsolete. As Beneficiary, I must be able to edit only case which is in Draft. |  | 2 |  |  |  |  | 1 | draft publish
1.03 |  | Preview a draft project/case - nice to have - dependancy with details page |  | As Beneficiary, I must be able to preview a case. |  | 3 |  |  | Display of commission setup, title, description, associated beneficiary
1.04 |  | Details View - Same - preview must use this screen layout | Title, Decription, Photos, Beneficiary details-photo,name,&commission, Donation Received | As visitor, I must be able to view details of a case. |  | 5 |  |  |  |  | 1
1.05 |  | Commission setup - as part of create and edit, view |  |  |  | 0
1.06 |  | Comments - flat | TBD | As visitor, I must be able to view and provide comments for a case by FB credentials. |  | 2
1.07 |  | Conversation - hierarchical | TBD
1.08 |  | Rating - (Review rate score, display rating average) | Show average rating, Show overlay to rate newly - rating and description can be provided and submited. (add/edit user rating) Only logedin user can rate a case. Otehrwise user will be asked to login. | As a visitor, I must be able to view average rating of a case. As a registered user, I must be able to rate a case along with description. As a registered user, I must be able to override my rating and rating description. |  | 5 |  |  | Rate star and a shortdescription |  | 2
1.09 |  | Rating history | Show review history below case content, reviews will be paginated (show more). clicking on rating count will be navigating the control to bottom of case content were the rating history displayed. | As a visitor, I must be able to view rating history and description. |  | 3 |  |  |  |  | 2
1.1 |  | Report abuse | only storing it on DB, only loged in user will be able to mark as abuse. Same user will be an update to the earlier comment. This is action for administrator. Admin function will need to take seperately. | As a registered user, I must be able to report a case as not genuine/abuse. |  | 2 |  |  |  |  | 2
1.11 |  | Share on social media - FB/Instagram/WhatsApp | Place FB share and Like button on case | As a visitor, I must be able to Like and/or share a case on Facebook/Instagram. |  | 2
1.12 |  | Like on social media - FB/Instagram/WhatsApp | NA - like and share can be done togather with 2 pointers
1.13 |  | Location and searchability | While creating the case, beneficiary should be abel to provide the location (address with all fields). Allow to change the location using pin from map, and store lat long in ddatabase. Location must be dieplayed on preview and case details page - with address on baloon. searchability not pat of this estimation. | As a Beneficiary, I must be able to provide geo location while creating a case. As a Beneficiary, I must be able to set and adjust geo location from map based on the address while creating a case so that it will be displayed in case page while viewing or previewing. |  | 3 |  |  |  |  | 2
1.14 |  | Upload Photos | Upload photos of a case, mark one are primary. Allow rearranging. Primary photo will be hoswin on tile. User should be able to remove added photo. There will be size limit. No picture adjustment feature required as part of this userstory. | As a Beneficiary, I must be able to upload photos of a case. As a Beneficiary, I must be able to rearrange photos uploaded. As a Beneficiary, I must be able to set a photo as primary. |  | 5 |  |  | Upload, Size, diamention, simple edit, cover photo, limit. |  | 2
1.15 |  | Upload Video, video url. | TBD, video url | [5 empty] | Upload, size, url?
1.16 |  | List - Recent and top rated. Relevant, Latest, popular,Top-rated, Location (near by), pagination | Home Page, filter: Published. Sort: Recent and top rated. Pagination. Pagination expands the list in home page itself. Filter/search is not part of this userstory. Fields: Title, Photo, Description, Beneficiary Name and photo, location. Caseid, beneficaryid. | As a visitor, I must be able to view list of published cases on home page. As a visitor, I must be able to view list of published cases on home page sorted by recent and top rated and paginated. |  | 5 |  |  | Define the scope |  | 2
1.17 |  | Donation - List, Total, lookup | Assume donation is already done. With this userstory we have to list the donations. Donor name, photo and donated amount, city and country name. x donors will be showin intially and howed more when clicking on show more. sort: donated amount | As a visitor, I must be able to view list of donors for a particular case. As a visitor, I must be able to view list of donors for a particular case sorted by donation amount.. |  | 3
1.18 |  | Payment options accepted | While creating a case, the beneficiary must opt the payment methodsaccepted. - TBD, needed clarity
1.19 |  | QR Code | N/A
1.2 |  | KYCs - specific to case | N/A
2 | Beneficiary Management |  |  |  | 1
2.01 |  | Beneficiary Register | N/A | [7 empty] | 2
2.02 |  | Profile view edit (my story), manage cases - Beneficiary listing. | Beneficiary: My story, benefactor:loan reason, occupationb, social media link. Part of profile edit and view profile | As a beneficiary, I must be able to provide my story which will be displayed to the site visitors on public profile. As a benefactor, I must be able to provide social media links which will be displayed to site visotors on public profile. As a benefactor, I must be able to provide 'loan reason' which will be displayed to site visotors on public profile. As a visitor, I must be able to view Beneficiary profile for a case. As a visitor, I must be able to view Benefactor/Donor profile for a case. |  | 2 |  |  |  |  | 3
2.03 |  | Beneficiary KYC management for payment options | N/A
2.04 |  | Beneficiary Profile public view | required | [7 empty] | 3
|  | Beneficiary Rating | Similar to case rating | As a visitor, I must be able to view average rating of a Beneficiary. As a registered user, I must be able to rate a beneficiary along with description. As a registered user, I must be able to override my rating and rating description for a beneficiary. As a visitor, I must be able to view rating history and description for a beneficiary. |  | 3
|  | Contact Beneficiary | Sending email to beneficiary, loged in suer data can be prefilled, but public user have to provide all details, in MVP no storing for contact us details. |  |  | 2
2.05 |  | Beneficiary Transaction tractability | TBD
2.05 |  | Beneficiary Contact me - email | TBD | [7 empty] | 3
3 | Benefactor Management |  |  |  | 1
3.01 |  | Benefactor Register
3.02 |  | Benefactor Profile edit (description), cases | [8 empty] | 2
3.03 |  | Benefactor Profile public view | [8 empty] | 3
3.04 |  | Benefactor Transaction tractability | required
3.05 |  | Benefactor Contact me - email | TBD | [7 empty] | 3
4 | Profile Management (common) |  |  |  | 1
4.01 |  | Login |  |  |  | 9 | M |  |  |  | 1
4.02 |  | Thirdparty login (FB, Goolge) | pavan |  | p:9,a:8,o:10(20),s:16-20+3 | 9 | L | 3 |  |  | 2
4.03 |  | Register | atul/om |  | a:5,o:(12),p:7(9),s:16-18 | 9 |  |  |  |  | 1
4.04 |  | Activate |  |  |  | 9 | S | 1 |  |  | 2
4.05 |  | View profile | om/atul/pavan |  | a:6,o:5,p:8,s:8 | 9 | M |  |  |  | 3
4.06 |  | Change Password |  |  |  | 9 |  |  |  |  | 3
4.07 |  | Forgot Password |  |  | a:8,p:12,o:12,s:16 | 9 |  |  |  |  | 3
5 | Customer Support |  | Happy fox |  | 3 | 28.6364 | p:5,a:5,o:7 |  |  |  | 5
5.01 |  | CS Submit a case - for customer support
5.02 |  | CS Conversation
5.03 |  | CS Chat Support
6 | Donation |  |  |  | 2 | [5 empty] | 4
6.01 |  | Donation breakdown/charges | [6 empty] | min max?, limit,
6.02 |  | Donation - inward
6.03 |  | Donation - payout (2 transactions)
6.04 |  | Transaction tractability
6.05 |  | Payment options - TBD | bitcoin
TBD Functional
7 |  | Non Functional
7.01 | Theme |  |  |  | 0 | [5 empty] | 0
7.01.1 |  | Color
7.01.2 |  | Fonts
7.01.3 |  | Logo, background image, etc.
7.01.4 |  | Title, Tagline, Texts
7.02 | Localization |  |  |  | 0 | [5 empty] | 0
7.02.1 |  | TBD
7.03 | File handling |  | IPFS |  | 0 | [5 empty] | 0
7.03.1 |  | TBD
7.04 | Spike on payment options |  |  |  | 0 | [5 empty] | 3
7.04.1 |  | TBD
7.05 | Logging |  |  |  | 1
7.05.1 |  | TBD
7.06 | Exception Handling |  |  |  | 1 | [5 empty] | 3
7.06.1 |  | TBD
7.07 | Authentication and Authorization |  |  |  | 0 | [5 empty] | 0
7.07.1 |  | Passport authentication
7.08 | Template handling - Email |  |  |  | 2 | [5 empty] | 3
7.08.1 |  | TBD
7.09 | Payment Gateway - multi tenancy |  |  |  | 1 |  |  |  | only case and related data wil be isolated |  | 3
7.09.1 |  | TBD
7.1 | Multi-tenancy - support |  |  |  | 1 | [5 empty] | 0
7.1.1 |  | TBD
7.2 | TBD Non Functional |  |  |  | 2

## Events
Pre kickoff (Thursday, 2019-JUN-12) | JUN12 - JUN21
1. Walkthrough of identified epics and userstories |  |  | User Self Service | Register | Login | Forgot Password | Change Password | Profile Edit
2. Set the priority/stack ranking |  |  | Beneficiary | Public Profile
3. Brainstorm for initial 3 sprints epics and userstories – a draft only |  |  | Benefactor | Public Profile
4. Breakdown during discussion if possible |  |  | Case | Create | Edit | View | List | Workflow | Review/Rating
Phase 0: Design phase (3-4 weeks, may extend also) | JUN17 - JUL12 |  | KYC Handling | Upload KYCs | Vew KYCs | KYC Workflow
1. Architecture design (ongoing) | MEANS |  | Payment | Methods | Payment | View | History | Logs
2. Infrastructure – identify Prod, Dev | AWS/S3 |  | Customer Support | Create Ticket | View Ticket | Ticket Workflow
3. Feasibility of technical required component(s) only | Inprogress |  | Tenant
4. Low level design for required component(s) only | Inprogress
5. Brainstorm for initial 3 sprints epics and userstories (2-3 iteration is possible) – finalization | Pending
6. Backlog grooming – reprioritize, identify the spikes, do further breakdown, size the user story | Pending
7. Framework development (at least mandatory components must be finished, rest all can be taken later in sprints as spikes) | Inprogress
Phase 1 onwards – sprints (2 weeks, iterative sprints)
1. Sprint planning and identify the goal | JUN12 - JUL19
2. Daily scrum/standup
3. Backlog grooming – reprioritize, identify the spikes, do further breakdown
4. Sprint review/demo
5. Sprint retrospective
Sprint 1 | JUL22 - AUG09 | Case listing, case view, beneficiary view, benefactor view
Sprint 2 | JUL12 - AUG30 | Case Onboarding, Show Location, Rate and Review, Show rating history, Donors and Donation Received
Sprint 3 | SEP02 - AUG20 | Case Upload and preview photos, discussion (FB), case-social media like and share, Payment-Cryptocurrency, QA
QA, Bugfixes
Sprint 4 | SEP23 - OCT11 | Payment integration pendings, Bug fixes, UAT
QA, UAT, Bugfixes
Sprint 5 | OCT14 - OCT31 | Support

## velocity and size matrix
admin tool
list recent cases
list marked as abuse
transaction tracability
|  | XS | S | M | L | XL | XXL
| min h | 1 | 3 | 5 | 8 | 13 | 21
| max h | 3 | 5 | 8 | 13 | 21 | 34
|  | XS | S | M | L | XL | XXL
| min h | 3 | 5 | 8 | 13 | 21 | 34
| max h | 5 | 8 | 13 | 21 | 34 | 55
variance

## references
oauth | Passport | http://www.passportjs.org/docs/